## PMBOK
| title | text | clean_text
0 | project risk management | project risk management includes the processes of conducting risk management planning, identification, analysis response planning, response implementation, and monitoring risk on a project. the objectives of project risk management are to increase the probability and/or impact of positive risks and to decrease the probability and/or impact of negative risks, in order to optimize the chances of project success. the project risk management processes are: identify risks—tthe process of identifying individual project risks as well as sources of overall project risk, ‘umenting their characteristics. 11.3 perform qualitative risk analysis—the process of prioritizing individual project risks for further analysis or action by assessing their probability of occurrence and impact as well as other characteristics. 11.4 perform quantitative risk analysis—tthe process of numerically analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives. 11.5 plan risk responses—the process of developing options, selecting strategies, and agreeing on actions 1 address overall project risk exposure, as well as to treat individual project risks. 11.6 implement risk responses—the process of implementing agreed-upon risk response plans. 11.7 monitor risks—the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. figure 11-1 provides an overview of the project risk management processes. the project management risk processes are presented as discrete processes with defined interfaces while, in practice, they overlap and interact in ways that cannot be completely detailed in this pmbok® guide. Figure 11-1. Project Risk Management Overview | project risk management include the process of conduct risk management planning , identification , analysisresponse planning , response implementation , and monitor risk on a project . the objective of project risk managementare to increase the probability and/or impact of positive risk and to decrease the probability and/or impact of negativerisks , in order to optimize the chance of project success.the project risk management process be : identify risks—tthe process of identify individual project risk as well a source of overall project risk , ‘ umenting their characteristics.11.3 perform qualitative risk analysis—the process of prioritize individual project risk for further analysisor action by assess their probability of occurrence and impact as well a other characteristics.11.4 perform quantitative risk analysis—tthe process of numerically analyze the combined effect of identifiedindividual project risk and other source of uncertainty on overall project objectives.11.5 plan risk responses—the process of develop option , select strategy , and agree on action 1address overall project risk exposure , as well a to treat individual project risks.11.6 implement risk responses—the process of implement agreed-upon risk response plans.11.7 monitor risks—the process of monitor the implementation of agreed-upon risk response plan , track identified risk , identify and analyze new risk , and evaluate risk process effectiveness throughoutthe project.figure 11-1 provide an overview of the project risk management process . the project management risk processesare present a discrete process with defined interface while , in practice , they overlap and interact in way thatcannot be completely detail in this pmbok guide.figure 11-1 . project risk management overview
1 | key concepts for project risk management | all projects are risky since they are unique undertakings with varying degrees of complexity that aim to deliver benefits. they do this in a context of constraints and assumptions, while responding to stakeholder expectations that may be conflicting and changing. organizations should choose to take project risk in a controlled and intentional manner in order to create value while balancing risk and reward. project risk management aims to identify and manage risks that are not addressed by the other project management processes. when unmanaged, these risks have the potential to cause the project to deviate from the plan and fail to achieve the defined project objectives. consequently, the effectiveness of project risk management is directly related to project success. risk exists at two levels within every project. each project contains individual risks that can affect the achievement of project objectives. it is also important to consider the riskiness of the overall project, which arises from the combination of individual project risks and other sources of uncertainty. project risk management processes address both levels of risk in projects, and these are defined as follows: @ individual project risk is an uncertain event or condition that, if it occurs, has a positive or negative effect on one or more project objectives. @ overall project risk is the effect of uncertainty on the project as a whole, arising from all sources of uncertainty including individual risks, representing the exposure of stakeholders to the implications of variations in project outcome, both positive and negative. individual project risks can have a positive or negative effect on project objectives if they occur. project risk management aims to exploit or enhance positive risks (opportunities) while avoiding or mitigating negative risks (threats). unmanaged threats may result in issues or problems such as delay, cost overruns, performance shortfall, or loss of reputation. opportunities that are captured can lead to benefits such as reduced time and cost, improved performance, or reputation. overall project risk can also be positive or negative. management of overall project risk aims to keep project risk sxposure within an acceptable range by reducing drivers of negative variation, promoting drivers of positive variation, and maximizing the probability of achieving overall project objectives. Risks will continue to emerge during the lifetime of the project, so Project Risk Management processes should be conducted iteratively. Risk is initially addressed during project planning by shaping the project strategy. Risk should also be monitored and managed as the project progresses to ensure that the project stays on track and emergent risks are addressed. In order to manage risk effectively on a particular project, the project team needs to know what level of risk exposure is acceptable in pursuit of the project objectives. This is defined by measurable risk thresholds that reflect the risk appetite of the organization and project stakeholders. Risk thresholds express the degree of acceptable variation around a project objective. They are explicitly stated and communicated to the project team and reflected in the definitions of risk imnact levels for the nroiject. | all project be risky since they be unique undertaking with vary degree of complexity that aim to deliverbenefits . they do this in a context of constraint and assumption , while respond to stakeholder expectation thatmay be conflict and change . organization should choose to take project risk in a controlled and intentional mannerin order to create value while balance risk and reward.project risk management aim to identify and manage risk that be not address by the other project managementprocesses . when unmanaged , these risk have the potential to cause the project to deviate from the plan and fail toachieve the defined project objective . consequently , the effectiveness of project risk management be directly relatedto project success.risk exists at two level within every project . each project contain individual risk that can affect the achievement ofproject objective . it be also important to consider the riskiness of the overall project , which arise from the combinationof individual project risk and other source of uncertainty . project risk management process address both level ofrisk in project , and these be define a follow : individual project risk be an uncertain event or condition that , if it occur , have a positive or negative effect onone or more project objective . overall project risk be the effect of uncertainty on the project a a whole , arise from all source of uncertaintyincluding individual risk , represent the exposure of stakeholder to the implication of variation in projectoutcome , both positive and negative.individual project risk can have a positive or negative effect on project objective if they occur . project riskmanagement aim to exploit or enhance positive risk ( opportunity ) while avoid or mitigate negative risk ( threat ) . unmanaged threat may result in issue or problem such a delay , cost overrun , performance shortfall , or loss of reputation . opportunity that be capture can lead to benefit such a reduced time and cost , improvedperformance , or reputation.overall project risk can also be positive or negative . management of overall project risk aim to keep project risksxposure within an acceptable range by reduce driver of negative variation , promote driver of positive variation , and maximize the probability of achieve overall project objectives.risks will continue to emerge during the lifetime of the project , so project risk management process should be conductediteratively . risk be initially addressed during project planning by shape the project strategy . risk should also be monitor andmanaged a the project progress to ensure that the project stay on track and emergent risk be addressed.in order to manage risk effectively on a particular project , the project team need to know what level of risk exposureis acceptable in pursuit of the project objectives . this be define by measurable risk threshold that reflect the riskappetite of the organization and project stakeholder . risk threshold express the degree of acceptable variation arounda project objective . they be explicitly state and communicate to the project team and reflect in the definition ofrisk imnact level for the nroiject .
2 | trends and emerging practices in project risk management | the focus of project risk management is broadening to ensure that all types of risk are considered, and that project risks are understood in a wider context. trends and emerging practices for project risk management include but are not limited to: @ non-event risks. most projects focus only on risks that are uncertain future events that may or may not occur. examples of event-based risks include: a key seller may go out of business during the project, the customer may change the requirement after design is complete, or a subcontractor may propose enhancements to the standard operating processes. there is an increasing recognition that non-event risks need to be identified and managed. there are two main types of non-event risks: = variability risk. uncertainty exists about some key characteristics of a planned event or activity or decision. examples of variability risks include: productivity may be above or below target, the number of errors found during testing may be higher or lower than expected, or unseasonal weather conditions may occur during the construction phase. m ambiguity risk. uncertainty exists about what might happen in the future. areas of the project where imperfect knowledge might affect the project’s ability to achieve its objectives include: elements of the requirement or technical solution, future developments in regulatory frameworks, or inherent systemic complexity in the project. Variability risks can be addressed using Monte Carlo analysis, with the range of variation reflected in probabili distributions, followed by actions to reduce the spread of possible outcomes. Ambiguity risks are managed b defining those areas where there is a deficit of knowledge or understanding, then filling the gap by obtainin expert external input or benchmarking against best practices. Ambiguity is also addressed through increment. development, prototyping, or simulation. @ Project resilience. The existence of emergent risk is becoming clear, with a growing awareness of so-called unknowable-unknowns. These are risks that can only be recognized after they have occurred. Emergent risks can be tackled through developing project resilience. This requires each project to have: @ Integrated risk management. Projects exist in an organizational context, and they may form part of a program Or portfolio. Risk exists at each of these levels, and risks should be owned and managed at the appropriate level. Some risks identified at higher levels will be delegated to the project team for management, and some project risks may be escalated to higher levels if they are best managed outside the project. A coordinated approach to enterprise-wide risk management ensures alignment and coherence in the way risk is managed across all levels. This builds risk efficiency into the structure of programs and portfolios, providing the greatest overall value for a given level of risk exposure. | the focus of project risk management be broaden to ensure that all type of risk be consider , and that projectrisks be understand in a wider context . trend and emerge practice for project risk management include but arenot limited to : non-event risk . most project focus only on risk that be uncertain future event that may or may not occur.examples of event-based risk include : a key seller may go out of business during the project , the customer maychange the requirement after design be complete , or a subcontractor may propose enhancement to the standardoperating processes.there be an increase recognition that non-event risk need to be identify and manage . there be two maintypes of non-event risk : = variability risk . uncertainty exist about some key characteristic of a planned event or activity or decision.examples of variability risk include : productivity may be above or below target , the number of error foundduring testing may be high or low than expect , or unseasonal weather condition may occur during theconstruction phase.m ambiguity risk . uncertainty exist about what might happen in the future . area of the project whereimperfect knowledge might affect the project ’ s ability to achieve it objective include : element of therequirement or technical solution , future development in regulatory framework , or inherent systemiccomplexity in the project.variability risk can be address use monte carlo analysis , with the range of variation reflect in probabilidistributions , follow by action to reduce the spread of possible outcome . ambiguity risk be manage bdefining those area where there be a deficit of knowledge or understanding , then fill the gap by obtaininexpert external input or benchmarking against best practice . ambiguity be also address through increment.development , prototyping , or simulation . project resilience . the existence of emergent risk be become clear , with a grow awareness of so-calledunknowable-unknowns . these be risk that can only be recognize after they have occur . emergent riskscan be tackle through develop project resilience . this require each project to have : integrate risk management . project exist in an organizational context , and they may form part of a programor portfolio . risk exists at each of these level , and risk should be own and manage at the appropriate level.some risk identify at high level will be delegate to the project team for management , and some projectrisks may be escalate to high level if they be best manage outside the project . a coordinated approach toenterprise-wide risk management ensure alignment and coherence in the way risk be manage across all levels.this build risk efficiency into the structure of program and portfolio , provide the great overall value for agiven level of risk exposure .
3 | tailoring considerations | because each project is unique, it is necessary to tailor the way project risk management processes are applied. considerations for tailoring include but are not limited to: @ project size. does the project’s size in terms of budget, duration, scope, or team size require a more detai approach to risk management? or is it small enough to justify a simplified risk process? @ project complexity. is a robust risk approach demanded by high levels of innovation, new technology, commercial arrangements, interfaces, or external dependencies that increase project complexity? or is the project simple enough that a reduced risk process will suffice? @ project importance. how strategically important is the project? is the level of risk increased for this project because it aims to produce breakthrough opportunities, addresses significant blocks to organizational performance, or involves major product innovation? @ development approach. is this a waterfall project, where risk processes can be followed sequentially and iteratively, or does the project follow an agile approach where risk is addressed at the start of each iteration as well as during its execution? tailoring of the project risk management processes to meet these considerations is part of the plan risk manageme process, and the outcomes of tailoring decisions are recorded in the risk management plan. | because each project be unique , it be necessary to tailor the way project risk management process be applied.considerations for tailor include but be not limit to : project size . do the project ’ s size in term of budget , duration , scope , or team size require a more detaiapproach to risk management ? or be it small enough to justify a simplified risk process ? project complexity . be a robust risk approach demand by high level of innovation , new technology , commercialarrangements , interface , or external dependency that increase project complexity ? or be the project simpleenough that a reduced risk process will suffice ? project importance . how strategically important be the project ? be the level of risk increase for this projectbecause it aim to produce breakthrough opportunity , address significant block to organizationalperformance , or involve major product innovation ? development approach . be this a waterfall project , where risk process can be follow sequentially anditeratively , or do the project follow an agile approach where risk be address at the start of each iteration aswell a during it execution ? tailoring of the project risk management process to meet these consideration be part of the plan risk managemeprocess , and the outcome of tailor decision be record in the risk management plan .
4 | considerations for agile/adaptive environments | high-variability environments, by definition, incur more uncertainty and risk. to address this, projects managed using adaptive approaches make use of frequent reviews of incremental work products and cross-functional project teams to accelerate knowledge sharing and ensure that risk is understood and managed. risk is considered when selecting the content of each iteration, and risks will also be identified, analyzed, and managed during each iteration. additionally, the requirements are kept as a living document that is updated regularly, and work ma as the project progresses, based on an improved understanding of current risk exposure. | high-variability environment , by definition , incur more uncertainty and risk . to address this , project manage usingadaptive approach make use of frequent review of incremental work product and cross-functional project team toaccelerate knowledge sharing and ensure that risk be understood and manage . risk be consider when select thecontent of each iteration , and risk will also be identify , analyze , and manage during each iteration.additionally , the requirement be keep a a living document that be update regularly , and work maas the project progress , base on an improved understanding of current risk exposure .
5 | 11.1 plan risk management | plan risk management is the process of defining how to conduct risk management activities for a project. the key benefit of this process is that it ensures that the degree, type, and visibility of risk management are proportionate to both risks and the importance of the project to the organization and other stakeholders. this process is performed once or at predefined points in the project. the inputs, tools and techniques, and outputs of the process are depicted in figure 11-2. figure 11-3 depicts the data flow diagram for the process. figure 11-2. plan risk management: inputs, tools & techniques, and outputs Figure 11-3. Plan Risk Management: Data Flow Diagram The Plan Risk Management process should begin when a project is conceived and should be completed early in the project. It may be necessary to revisit this process later in the project life cycle, for example at a major phase change, or if the project scope changes significantly, or if a subsequent review of risk management effectiveness determines that the Project Risk Management process requires modification. | plan risk management be the process of define how to conduct risk management activity for a project . the keybenefit of this process be that it ensure that the degree , type , and visibility of risk management be proportionate to bothrisks and the importance of the project to the organization and other stakeholder . this process be perform once orat predefined point in the project . the input , tool and technique , and output of the process be depict in figure11-2 . figure 11-3 depict the data flow diagram for the process.figure 11-2. plan risk management : input , tool & technique , and outputsfigure 11-3 . plan risk management : data flow diagramthe plan risk management process should begin when a project be conceive and should be complete early in theproject . it may be necessary to revisit this process later in the project life cycle , for example at a major phase change , orif the project scope change significantly , or if a subsequent review of risk management effectiveness determine thatthe project risk management process require modification .
6 | 11.1.1 plan risk management: inputs
7 | 11.1.1.1 project charter
8 | 11.1.1.2 project management plan | described in section 4.2.3.1. in planning project risk management, all approved subsidiary management plan should be taken into consideration in order to make the risk management plan consistent with them. the methodolog outlined in other project management plan components might influence the plan risk management process. | describe in section 4.2.3.1. in planning project risk management , all approve subsidiary management planshould be take into consideration in order to make the risk management plan consistent with them . the methodologoutlined in other project management plan component might influence the plan risk management process .
9 | 11.1.1.3 project documents | project documents that can be considered as inputs for this process include but are not limited to the stakehold register as described in section 13.1.3.1. the stakeholder register contains details of the project’s stakeholders ai provides an overview of their project roles and their attitude toward risk on this project. this is useful in determini roles and responsibilities for managing risk on the project, as well as setting risk thresholds for the project. | project document that can be consider a input for this process include but be not limit to the stakeholdregister a describe in section 13.1.3.1. the stakeholder register contain detail of the project ’ s stakeholder aiprovides an overview of their project role and their attitude toward risk on this project . this be useful in determiniroles and responsibility for manage risk on the project , as well a set risk threshold for the project .
10 | 11.1.1.4 enterprise environmental factors | the enterprise environmental factors that can influence the plan risk management process include but are not limited to overall risk thresholds set by the organization or key stakeholders. | the enterprise environmental factor that can influence the plan risk management process include but be notlimited to overall risk threshold set by the organization or key stakeholder .
11 | 11.1.1.5 organizational process assets | the organizational process assets that can influence the plan risk management process include but are not limited to: the www. @ organizational risk policy; @ risk categories, possibly organized into a risk breakdown str @ common definitions of risk concepts and terms; @ risk statement formats; @ templates for the risk management plan, risk register, and ri @ roles and responsibilities; @ authority levels for decision making; and @ lessons learned repository from previous similar projects. | the organizational process asset that can influence the plan risk management process include but be notlimited to : the www . organizational risk policy ; risk category , possibly organize into a risk breakdown str common definition of risk concept and term ; risk statement format ; template for the risk management plan , risk register , and ri role and responsibility ; authority level for decision making ; and lesson learn repository from previous similar project .
12 | 11.1.2 plan risk management: tools and techniques
13 | 11.1.2.1 expert judgment
14 | 11.1.2.2 data analysis
15 | 11.1.2.3 meetings | the risk management plan may be developed as part of the project kick-off meeting or a specific planning meeting may be held. attendees may include the project manager, selected project team members, key stakeholders, or team members who are responsible to manage the risk management process on the project. others outside the organization may also be invited, as needed, including customers, sellers, and regulators. a skilled facilitator can help participants remain focused on the task, agree on key aspects of the risk approach, identify and overcome sources of bias, and resolve any disagreements that may arise. | the risk management plan may be develop a part of the project kick-off meeting or a specific planning meetingmay be hold . attendee may include the project manager , select project team member , key stakeholder , or teammembers who be responsible to manage the risk management process on the project . others outside the organizationmay also be invite , a need , include customer , seller , and regulator . a skilled facilitator can help participantsremain focus on the task , agree on key aspect of the risk approach , identify and overcome source of bias , andresolve any disagreement that may arise .
16 | 11.1.3 plan risk management: outputs
17 | 11.1.3.1 risk management plan | @ risk strategy. describes the general approach to managing risk on this project. > roles and responsibilities. defines the lead, support, and risk management team members for each type c activity described in the risk management plan, and clarifies their responsibilities. @ funding. identifies the funds needed to perform activities related to project risk management. establist protocols for the application of contingency and management reserves. @ timing. defines when and how often the project risk management processes will be performed throughou project life cycle, and establishes risk management activities for inclusion into the project schedule. @ risk categories. provide a means for grouping individual project risks. a common way to structure risk categories is with a risk breakdown structure (rbs), which is a hierarchical representation of potential sources of risk (see example in figure 11-4). an rbs helps the project team consider the full range of sources from which individual project risks may arise. this can be useful when identifying risks or when categorizing identified risks. the organization may have a generic rbs to be used for all projects, or there may be several rbs frameworks for different types of projects, or the project may develop a tailored rbs. where an rbs is not used, an organization may use a custom risk categorization framework, which may take the form of a simple list of categories or a structure based on project objectives. Figure 11-4. Extract from Sample Risk Breakdown Structure (RBS) @ Stakeholder risk appetite. The risk appetites of key stakeholders on the project are recorded in the ris’ management plan, as they inform the details of the Plan Risk Management process. In particular, stakeholder ris appetite should be expressed as measurable risk thresholds around each project objective. These thresholds wi determine the acceptable level of overall project risk exposure, and they are also used to inform the definitions c probability and impacts to be used when assessing and prioritizing individual project risks. @ Definitions of risk probability and impacts. Definitions of risk probability and impact levels are specific to the project context and reflect the risk appetite and thresholds of the organization and key stakeholders. The project may generate specific definitions of probability and impact levels or it may start with general definitions provided by the organization. The number of levels reflects the degree of detail required for the Project Risk Management process, with more levels used for a more detailed risk approach (typically five levels), and fewer for a simple process (usually three). Table 11-1 provides an example of definitions of probability and impacts against three project objectives. These scales can be used to evaluate both threats and opportunities by interpreting the impact definitions as negative for threats (delay, additional cost, and performance shortfall) and positive for opportunities (reduced time or cost, and performance enhancement). Table 11-1. Example of Definitions for Probability and Impacts @ Probability and impact matrix. Described in Section 11.3.2.6. Prioritization rules may be specified by the organization in advance of the project and be included in organizational process assets, or they may be tailored to the specific project. Opportunities and threats are represented in a common probability and impact matrix using positive definitions of impact for opportunities and negative impact definitions for threats. Descriptive terms (such as very high, high, medium, low, and very low) or numeric values can be used for probability and impact. Where numeric values are used, these can be multiplied to give a probability-impact score for each risk, which allows the relative priority of individual risks to be evaluated within each priority level. An example probability and impact matrix is presented in Figure 11-5, which also shows a possible numeric risk scoring scheme. Figure 11-5. Example Probability and Impact Matrix with Scoring Scheme @ Reporting formats. Reporting formats define how the outcomes of the Project Risk Management process will be documented, analyzed, and communicated. This section of the risk management plan describes the content and format of the risk register and the risk report, as well as any other required outputs from the Project Risk Management processes. | risk strategy . describe the general approach to manage risk on this project. > role and responsibility . define the lead , support , and risk management team member for each type cactivity describe in the risk management plan , and clarifies their responsibility . funding . identify the fund need to perform activity relate to project risk management . establistprotocols for the application of contingency and management reserve . timing . defines when and how often the project risk management process will be perform throughouproject life cycle , and establishes risk management activity for inclusion into the project schedule . risk category . provide a mean for group individual project risk . a common way to structure risk categoriesis with a risk breakdown structure ( rb ) , which be a hierarchical representation of potential source of risk ( seeexample in figure 11-4 ) . an rb help the project team consider the full range of source from which individualproject risk may arise . this can be useful when identify risk or when categorize identify risk . theorganization may have a generic rb to be use for all project , or there may be several rb framework fordifferent type of project , or the project may develop a tailored rb . where an rb be not use , an organizationmay use a custom risk categorization framework , which may take the form of a simple list of category or astructure base on project objectives.figure 11-4 . extract from sample risk breakdown structure ( rb ) stakeholder risk appetite . the risk appetite of key stakeholder on the project be record in the ri ’ management plan , a they inform the detail of the plan risk management process . in particular , stakeholder risappetite should be express a measurable risk threshold around each project objective . these threshold widetermine the acceptable level of overall project risk exposure , and they be also use to inform the definition cprobability and impact to be use when assess and prioritize individual project risk . definition of risk probability and impact . definition of risk probability and impact level be specific to theproject context and reflect the risk appetite and threshold of the organization and key stakeholder . the projectmay generate specific definition of probability and impact level or it may start with general definition providedby the organization . the number of level reflect the degree of detail require for the project risk managementprocess , with more level use for a more detailed risk approach ( typically five level ) , and few for a simpleprocess ( usually three ) . table 11-1 provide an example of definition of probability and impact against threeproject objective . these scale can be use to evaluate both threat and opportunity by interpret the impactdefinitions a negative for threat ( delay , additional cost , and performance shortfall ) and positive for opportunity ( reduced time or cost , and performance enhancement ) .table 11-1 . example of definition for probability and impact probability and impact matrix . describe in section 11.3.2.6 . prioritization rule may be specify by theorganization in advance of the project and be include in organizational process asset , or they may be tailor tothe specific project . opportunity and threat be represent in a common probability and impact matrix usingpositive definition of impact for opportunity and negative impact definition for threat . descriptive term ( such a very high , high , medium , low , and very low ) or numeric value can be use for probability and impact.where numeric value be use , these can be multiply to give a probability-impact score for each risk , whichallows the relative priority of individual risk to be evaluate within each priority level . an example probability andimpact matrix be present in figure 11-5 , which also show a possible numeric risk score scheme.figure 11-5 . example probability and impact matrix with score scheme reporting format . report format define how the outcome of the project risk management process willbe document , analyze , and communicate . this section of the risk management plan describe the contentand format of the risk register and the risk report , as well a any other require output from the project riskmanagement process .
18 | 11.2 identify risks | identify risks is the process of identifying individual project risks as well as sources of overall project risk, and documenting their characteristics. the key benefit of this process is the documentation of existing individual project risks and the sources of overall project risk. it also brings together information so the project team can respond appropriately to identified risks. this process is performed throughout the project. the inputs, tools and techniques, and outputs of the process are depicted in figure 11-6. figure 11-7 depicts the data flow diagram for the process. figure 11-6. identify risks: inputs, tools & techniques, and outputs Figure 11-7. Identify Risks: Data Flow Diagram Identify Risks considers both individual project risks and sources of overall project risk. Participants in risk identification activities may include the following: project manager, project team members, project risk specialist (if assigned), customers, subject matter experts from outside the project team, end users, other project managers, operations managers, stakeholders, and risk management experts within the organization. While these personnel are often key participants for risk identification, all project stakeholders should be encouraged to identify individual project risks. It is particularly important to involve the project team so they can develop and maintain a sense of ownership and responsibility for identified individual project risks, the level of overall project risk, and associated risk response actions. When describing and recording individual project risks, a consistent format should be used for risk statements to ensure that each risk is understood clearly and unambiguously in order to support effective analysis and risk response development. Risk owners for individual project risks may be nominated as part of the Identify Risks process, and will be confirmed during the Perform Qualitative Risk Analysis process. Preliminary risk responses may also be identified and recorded and will be reviewed and confirmed as part of the Plan Risk Responses process. Identify Risks is an iterative process, since new individual project risks may emerge as the project progresses through S life cycle and the level of overall project risk will also change. The frequency of iteration and participation in each risk lentification cycle will vary by situation, and this will be defined in the risk management plan. | identify risk be the process of identify individual project risk as well a source of overall project risk , anddocumenting their characteristic . the key benefit of this process be the documentation of exist individual project risksand the source of overall project risk . it also bring together information so the project team can respond appropriatelyto identified risk . this process be perform throughout the project . the input , tool and technique , and output of theprocess be depict in figure 11-6. figure 11-7 depict the data flow diagram for the process.figure 11-6. identify risk : input , tool & technique , and outputsfigure 11-7 . identify risk : data flow diagramidentify risk considers both individual project risk and source of overall project risk . participant in riskidentification activity may include the following : project manager , project team member , project risk specialist ( if assign ) , customer , subject matter expert from outside the project team , end user , other project manager , operation manager , stakeholder , and risk management expert within the organization . while these personnel areoften key participant for risk identification , all project stakeholder should be encourage to identify individual projectrisks . it be particularly important to involve the project team so they can develop and maintain a sense of ownership andresponsibility for identified individual project risk , the level of overall project risk , and associate risk response actions.when describe and record individual project risk , a consistent format should be use for risk statement toensure that each risk be understood clearly and unambiguously in order to support effective analysis and risk responsedevelopment . risk owner for individual project risk may be nominate a part of the identify risk process , and willbe confirm during the perform qualitative risk analysis process . preliminary risk response may also be identifiedand record and will be review and confirm a part of the plan risk responses process.identify risk be an iterative process , since new individual project risk may emerge a the project progress throughs life cycle and the level of overall project risk will also change . the frequency of iteration and participation in each risklentification cycle will vary by situation , and this will be define in the risk management plan .
19 | 11.2.1 identify risks: inputs
20 | 11.2.1.1 project management plan
21 | 11.2.1.1 project management plan | described in section 4.2.3.1. project management plan components include but are not limited to: @ quality management plan. described in section 8.1.3.1. the quality management plan may identify areas that are subject to uncertainty or ambiguity, or where key assumptions have been made that might give rise to risk. @ resource management plan. described in section 9.1.3.1. the resource management plan may identify areas that are subject to uncertainty or ambiguity, or where key assumptions have been made that might give rise to risk. @ Risk management plan. Described in Section 11.1.3.1. The risk management plan provides information on risk-related roles and responsibilities, indicates how risk management activities are included in the budget and schedule, and describes categories of risk, which may be expressed as a risk breakdown structure (Figure 11-4). @ Scope baseline. Described in Section 5.4.3.1. The scope baseline includes deliverables and criteria for their acceptance, some of which might give rise to risk. It also contains the WBS, which can be used as a framework to structure risk identification techniques. @ Schedule baseline. Described in Section 6.5.3.1. The schedule baseline may be reviewed to identify milestones and deliverable due dates that are subject to uncertainty or ambiguity, or where key assumptions have been made that might give rise to risk. @ Cost baseline. Described in Section 7.3.3.1. The cost baseline may be reviewed to identify costs or funding requirements that are subject to uncertainty or ambiguity, or where key assumptions have been made that might give rise to risk. | describe in section 4.2.3.1. project management plan component include but be not limit to : quality management plan . describe in section 8.1.3.1. the quality management plan may identify area thatare subject to uncertainty or ambiguity , or where key assumption have be make that might give rise to risk . resource management plan . describe in section 9.1.3.1. the resource management plan may identifyareas that be subject to uncertainty or ambiguity , or where key assumption have be make that might giverise to risk . risk management plan . describe in section 11.1.3.1 . the risk management plan provide information onrisk-related role and responsibility , indicate how risk management activity be include in the budget andschedule , and describes category of risk , which may be express a a risk breakdown structure ( figure 11-4 ) . scope baseline . describe in section 5.4.3.1 . the scope baseline include deliverable and criterion for theiracceptance , some of which might give rise to risk . it also contain the wb , which can be use a a frameworkto structure risk identification technique . schedule baseline . describe in section 6.5.3.1 . the schedule baseline may be review to identify milestonesand deliverable due date that be subject to uncertainty or ambiguity , or where key assumption have beenmade that might give rise to risk . cost baseline . describe in section 7.3.3.1 . the cost baseline may be review to identify cost or fundingrequirements that be subject to uncertainty or ambiguity , or where key assumption have be make that mightgive rise to risk .
22 | 11.2.1.2 project documents | project documents that can be considered as inputs for this process include but are not limited to: @ assumption log. described in section 4.1.3.2. assumptions and constraints recorded in the assumpt give rise to individual project risks and may also influence the level of overall project risk. @ cost estimates. described in section 7.2.3.1. cost estimates provide quantitative assessments of project costs, ideally expressed as a range, indicating the degree of risk, where a structured review of the documents may indicate that the current estimate is insufficient and poses a risk to the project. @ duration estimates. described in section 6.4.3.1. duration estimates provide quantitative assessments of project durations, ideally expressed as a range, indicating the degree of risk, where a structured review of the documents may indicate that the current estimate is insufficient and poses a risk to the project. essons learned register. described in section 4.4.3.1. lessons learned about risk identified from earlier phases the project are reviewed to determine whether similar risks might recur during the remainder of the project. @ Resource requirements. Described in Section 9.2.3.1. Resource requirements provide quantitative assessments of project resource requirements, ideally expressed as a range, indicating the degree of risk, where a structured review of the documents may indicate that the current estimate is insufficient and poses a risk to the project. @ Stakeholder register. Described in Section 13.1.3.1. The stakeholder register indicates which individuals or groups might participate in identifying risks to the project. It also details those individuals who are available to act as risk owners. | project document that can be consider a input for this process include but be not limit to : assumption log . describe in section 4.1.3.2. assumption and constraint record in the assumptgive rise to individual project risk and may also influence the level of overall project risk . cost estimate . describe in section 7.2.3.1. cost estimate provide quantitative assessment of project cost , ideally express a a range , indicate the degree of risk , where a structured review of the document mayindicate that the current estimate be insufficient and pose a risk to the project . duration estimate . describe in section 6.4.3.1. duration estimate provide quantitative assessment ofproject duration , ideally express a a range , indicate the degree of risk , where a structured review of thedocuments may indicate that the current estimate be insufficient and pose a risk to the project.essons learn register . describe in section 4.4.3.1. lesson learn about risk identify from early phasesthe project be review to determine whether similar risk might recur during the remainder of the project . resource requirement . describe in section 9.2.3.1 . resource requirement provide quantitativeassessments of project resource requirement , ideally express a a range , indicate the degree of risk , where a structured review of the document may indicate that the current estimate be insufficient and posesa risk to the project . stakeholder register . describe in section 13.1.3.1 . the stakeholder register indicate which individual orgroups might participate in identify risk to the project . it also detail those individual who be available toact a risk owner .
23 | 11.2.1.3 agreements | described in section 12.2.3.2. if the project requires external procurement of resources, the agreements may have information such as milestone dates, contract type, acceptance criteria, and awards and penalties that can present threats or opportunities. | describe in section 12.2.3.2. if the project require external procurement of resource , the agreement may haveinformation such a milestone date , contract type , acceptance criterion , and award and penalty that can presentthreats or opportunity .
24 | 11.2.1.4 procurement documentation | described in section 12.3.1.4. if the project requires external procurement of resources, the initial procurement documentation should be reviewed as procuring goods and services from outside the organization may increase or decrease overall project risk and may introduce additional individual project risks. as the procurement documentation is updated throughout the project, the most up to date documentation can be reviewed for risks. for example, seller performance reports, approved change requests and information on inspections. | describe in section 12.3.1.4. if the project require external procurement of resource , the initial procurementdocumentation should be review a procure good and service from outside the organization may increase ordecrease overall project risk and may introduce additional individual project risk . a the procurement documentationis update throughout the project , the most up to date documentation can be review for risk . for example , sellerperformance report , approve change request and information on inspection .
25 | 11.2.1.5 enterprise environmental factors | vironmental factors that can influence the identify risks process include but are not limited to: @ published material, including commercial risk databases or checklists, @ nradamir ctiidiac | vironmental factor that can influence the identify risk process include but be not limit to : publish material , include commercial risk database or checklist , nradamir ctiidiac
26 | 11.2.1.6 organizational process assets | 11.2.1.6 organizational process assets the organizational process assets that can influer @ project files, including actual data, @ organizational and project process controls, @ risk statement formats, and @ checklists from previous similar projects. the organizational process assets that can influence the identify risks process include but are not limited to: @ project files, including actual data, @ organizational and project process controls, a dial atatamant farmata an | 11.2.1.6 organizational process assetsthe organizational process asset that can influer project file , include actual data , organizational and project process control , risk statement format , and checklist from previous similar projects.the organizational process asset that can influence the identify risk process include but be not limit to : project file , include actual data , organizational and project process control , a dial atatamant farmata an
27 | 11.2.2 identify risks: tools and techniques
28 | 11.2.2.1 expert judgment | described in section 4.1.2.1. expertise should be considered from individuals or groups with specialized knowl of similar projects or business areas. such experts should be identified by the project manager and invited to con: all aspects of individual project risks as well as sources of overall project risk, based on their previous experience areas of expertise. the experts’ bias should be taken into account in this process. | describe in section 4.1.2.1. expertise should be consider from individual or group with specialized knowlof similar project or business area . such expert should be identify by the project manager and invite to con : all aspect of individual project risk as well a source of overall project risk , base on their previous experienceareas of expertise . the expert ’ bias should be take into account in this process .
29 | 11.2.2.2 data gathering | data-gathering techniques that can be used for this process include but are not limited to: @ brainstorming. the goal of brainstorming (see section 4.1.2.2) is to obtain a comprehensive list of individual project risks and sources of overall project risk. the project team usually performs brainstorming, often with a multidisciplinary set of experts who are not part of the team. ideas are generated under the guidance of a facilitator, either in a free-form brainstorm session or one that uses more structured techniques. categories of risk, such as in a risk breakdown structure, can be used as a framework. particular attention should be paid to ensuring that risks identified through brainstorming are clearly described, since the technique can result in ideas that are not fully formed. ullal alt pul tuny iulitiou. @ checklists. a checklist is a list of items, actions, or points to be considered. it is often used as a reminder. risk checklists are developed based on historical information and knowledge that has been accumulated from similar projects and from other sources of information. they are an effective way to capture lessons learned from similar completed projects, listing specific individual project risks that have occurred previously and that may be relevant to this project. the organization may maintain a risk checklist based on its own completed projects or may use generic risk checklists from the industry. while a checklist may be quick and simple to use, itis impossible to build an exhaustive one, and care should be taken to ensure the checklist is not used to avoid the effort of proper risk identification. the project team should also explore items that do not appear on the checklist. additionally, the checklist should be reviewed from time to time to update new information as well as remove or archive obsolete information. a intaruinwuse indisigdiial nrnainant rieloa and aniirnnn anf narall nraiant ricl nan ha idantitinn hus intannaunnn avnonriannngs @ interviews. individual project risks and sources of overall project risk can be identified by interviewing experience project participants, stakeholders, and subject matter experts. interviews (see section 5.2.2.2) should b conducted in an environment of trust and confidentiality to encourage honest and unbiased contributions. | data-gathering technique that can be use for this process include but be not limit to : brainstorming . the goal of brainstorming ( see section 4.1.2.2 ) be to obtain a comprehensive list of individualproject risk and source of overall project risk . the project team usually perform brainstorming , often witha multidisciplinary set of expert who be not part of the team . idea be generate under the guidance of afacilitator , either in a free-form brainstorm session or one that use more structured technique . category ofrisk , such a in a risk breakdown structure , can be use a a framework . particular attention should be pay toensuring that risk identify through brainstorming be clearly describe , since the technique can result in ideasthat be not fully formed.ullal alt pul tuny iulitiou . checklist . a checklist be a list of item , action , or point to be consider . it be often use a a reminder.risk checklist be develop base on historical information and knowledge that have be accumulate fromsimilar project and from other source of information . they be an effective way to capture lesson learnedfrom similar complete project , list specific individual project risk that have occur previously and thatmay be relevant to this project . the organization may maintain a risk checklist base on it own completedprojects or may use generic risk checklist from the industry . while a checklist may be quick and simple to use , itis impossible to build an exhaustive one , and care should be take to ensure the checklist be not use to avoidthe effort of proper risk identification . the project team should also explore item that do not appear on thechecklist . additionally , the checklist should be review from time to time to update new information a well asremove or archive obsolete information.a intaruinwuse indisigdiial nrnainant rieloa and aniirnnn anf narall nraiant ricl nan ha idantitinn hus intannaunnn avnonriannngs interview . individual project risk and source of overall project risk can be identify by interview experienceproject participant , stakeholder , and subject matter expert . interview ( see section 5.2.2.2 ) should bconducted in an environment of trust and confidentiality to encourage honest and unbiased contribution .
30 | 11.2.2.3 data analysis | data analysis techniques that can be used for this process include but are not limited to: @ root cause analysis. root cause analysis (see section 8.2.2.2) is typically used to discover the underlying causes that lead to a problem, and develop preventive action. it can be used to identify threats by starting with a problem statement (for example, the project might be delayed or over budget) and exploring which threats might result in that problem occurring. the same technique can be used to find opportunities by starting with a benefit statement (for example, early delivery or under budget) and exploring which opportunities might result in that hanoafit hoinn roalizan @ assumption and constraint analysis. every project and its project management plan are conceived and developed based on a set of assumptions and within a series of constraints. these are often already incorporated in the scope baseline and project estimates. assumption and constraint analysis explores the validity of assumptions and constraints to determine which pose a risk to the project. threats may be identified from the inaccuracy, instability, inconsistency, or incompleteness of assumptions. constraints may give rise to opportunities through removing or relaxing a limiting factor that affects the execution of a project or process. @ swot analysis. this technique examines the project from each of the strengths, weaknesses, opportunities, and threats (swot) perspectives. for risk identification, it is used to increase the breadth of identified risks by including internally generated risks. the technique starts with the identification of strengths and weaknesses of the organization, focusing on either the project, organization, or the business area in general. swot analysis then identifies any opportunities for the project that may arise from strengths, and any threats resulting from weaknesses. the analysis also examines the degree to which organizational strengths may offset threats and determines if weaknesses might hinder opportunities. @ document analysis. described in section 5.2.2.3. risks may be identified from a structured review of projec’ documents, including, but not limited to, plans, assumptions, constraints, previous project files, contracts agreements, and technical documentation. uncertainty or ambiguity in project documents, as well as inconsistencies within a document or between different documents, may be indicators of risk on the project. | data analysis technique that can be use for this process include but be not limit to : root cause analysis . root cause analysis ( see section 8.2.2.2 ) be typically use to discover the underlyingcauses that lead to a problem , and develop preventive action . it can be use to identify threat by start with aproblem statement ( for example , the project might be delay or over budget ) and explore which threat mightresult in that problem occur . the same technique can be use to find opportunity by start with a benefitstatement ( for example , early delivery or under budget ) and explore which opportunity might result in thathanoafit hoinn roalizan assumption and constraint analysis . every project and it project management plan be conceivedand developed base on a set of assumption and within a series of constraint . these be often alreadyincorporated in the scope baseline and project estimate . assumption and constraint analysis explore thevalidity of assumption and constraint to determine which pose a risk to the project . threat may be identifiedfrom the inaccuracy , instability , inconsistency , or incompleteness of assumption . constraint may give rise toopportunities through remove or relax a limiting factor that affect the execution of a project or process . swot analysis . this technique examine the project from each of the strength , weakness , opportunity , and threat ( swot ) perspectives . for risk identification , it be use to increase the breadth of identified risk byincluding internally generate risk . the technique start with the identification of strength and weaknessesof the organization , focus on either the project , organization , or the business area in general . swot analysisthen identify any opportunity for the project that may arise from strength , and any threat result fromweaknesses . the analysis also examine the degree to which organizational strength may offset threat anddetermines if weakness might hinder opportunity . document analysis . describe in section 5.2.2.3. risk may be identify from a structured review of projec ’ document , include , but not limited to , plan , assumption , constraint , previous project file , contractsagreements , and technical documentation . uncertainty or ambiguity in project document , as well asinconsistencies within a document or between different document , may be indicator of risk on the project .
31 | 11.2.2.4 interpersonal and team skills | interpersonal and team skills that can be used for this process includes but are not limited to facilitation (see section 4.1.2.3). facilitation improves the effectiveness of many of the techniques used to identify individual project risks and sources of overall project risk. a skilled facilitator can help participants remain focused on the risk identification task, follow the method associated with the technique accurately, ensure clear risk descriptions, identify and overcome sources of bias. and resolve anv disagreements that may arise. | interpersonal and team skill that can be use for this process include but be not limit to facilitation ( see section4.1.2.3 ) . facilitation improve the effectiveness of many of the technique use to identify individual project risk andsources of overall project risk . a skilled facilitator can help participant remain focused on the risk identification task , follow the method associate with the technique accurately , ensure clear risk description , identify and overcomesources of bias . and resolve anv disagreement that may arise .
32 | 11.2.2.5 prompt lists | a prompt list is a predetermined list of risk categories that might give rise to individual project risks and that could also act as sources of overall project risk. the prompt list can be used as a framework to aid the project team in idea generation when using risk identification techniques. the risk categories in the lowest level of the risk breakdown structure can be used as a prompt list for individual project risks. some common strategic frameworks are more suitable for identifying sources of overall project risk, for example pestle (political, economic, social, technological, legal, environmental), tecop (technical, environmental, commercial, operational, political), or vuca (volatility, uncertainty, complexity, ambiguity). | a prompt list be a predetermined list of risk category that might give rise to individual project risk and that could alsoact a source of overall project risk . the prompt list can be use a a framework to aid the project team in idea generationwhen use risk identification technique . the risk category in the low level of the risk breakdown structure can beused a a prompt list for individual project risk . some common strategic framework be more suitable for identifyingsources of overall project risk , for example pestle ( political , economic , social , technological , legal , environmental ) , tecop ( technical , environmental , commercial , operational , political ) , or vuca ( volatility , uncertainty , complexity , ambiguity ) .
33 | 11.2.2.6 meetings | to undertake risk identification, the project team may conduct a specialized meeting (often called a risk workshop). most risk workshops include some form of brainstorming (see section 4.1.2.2), but other risk identification techniques may be included depending on the level of the risk process defined in the risk management plan. use of a skilled facilitator will increase the effectiveness of the meeting. it is also essential to ensure that the right people participate in the risk workshop. on larger projects, it may be appropriate to invite the project sponsor, subject matter experts, sellers, representatives of the customer, or other project stakeholders. risk workshops for smaller projects may be restricted to a subset of the project team. | to undertake risk identification , the project team may conduct a specialized meeting ( often call a risk workshop ) .most risk workshop include some form of brainstorming ( see section 4.1.2.2 ) , but other risk identification techniquesmay be include depend on the level of the risk process define in the risk management plan . use of a skilledfacilitator will increase the effectiveness of the meeting . it be also essential to ensure that the right people participate inthe risk workshop . on large project , it may be appropriate to invite the project sponsor , subject matter expert , seller , representative of the customer , or other project stakeholder . risk workshop for small project may be restrict toa subset of the project team .
34 | 11.2.3 identify risks: outputs
35 | 11.2.3.1 risk register | the risk register captures details of identified individual project risks. the results of perform qualitative risk analysis, plan risk responses, implement risk responses, and monitor risks are recorded in the risk register as those processes are conducted throughout the project. the risk register may contain limited or extensive risk information depending on project variables such as size and complexity. @ list of identified risks. each individual project risk is given a unique identifier in the risk register. identified risks are described in as much detail as required to ensure unambiguous understanding. a structured risk statement may be used to distinguish risks from their cause(s) and their effect(s). @ potential risk owners. where a potential risk owner has been identified during the identify risks process, the risk owner is recorded in the risk register. this will be confirmed during the perform qualitative risk analysis process. additional data may be recorded for each identified risk, depending on the risk register format specified in the risk management plan. this may include: a short risk title, risk category, current risk status, one or more causes, one or more effects on objectives, risk triggers (events or conditions that indicate that a risk is about to occur), wbs reference of affected activities, and timing information (when was the risk identified, when might the risk occur, when might it no longer be relevant, and what is the deadline for taking action). | the risk register capture detail of identified individual project risk . the result of perform qualitative risk analysis , plan risk response , implement risk response , and monitor risk be record in the risk register a those processesare conduct throughout the project . the risk register may contain limited or extensive risk information depend onproject variable such a size and complexity . list of identified risk . each individual project risk be give a unique identifier in the risk register . identify risksare describe in as much detail a require to ensure unambiguous understanding . a structured risk statementmay be use to distinguish risk from their cause ( s ) and their effect ( s ) . potential risk owner . where a potential risk owner have be identify during the identify risk process , therisk owner be record in the risk register . this will be confirm during the perform qualitative risk analysisprocess.additional data may be record for each identify risk , depend on the risk register format specify in the riskmanagement plan . this may include : a short risk title , risk category , current risk status , one or more cause , one ormore effect on objective , risk trigger ( event or condition that indicate that a risk be about to occur ) , wbs referenceof affect activity , and time information ( when be the risk identify , when might the risk occur , when might it nolonger be relevant , and what be the deadline for take action ) .
36 | 11.2.3.2 risk report | the risk report presents information on sources of overall project risk, together with summary information on identifie individual project risks. the risk report is developed progressively throughout the project risk management process. th results of perform qualitative risk analysis, perform quantitative risk analysis, plan risk responses, implement ris responses, and monitor risks are also included in the risk report as those processes are completed. on completion ¢ the identify risks process, information in the risk report may include but is not limited to: summary information on identified individual project risks, such as number of identified threats and opportunitie listribution of risks across risk categories, metrics and trends, etc. | the risk report present information on source of overall project risk , together with summary information on identifieindividual project risk . the risk report be develop progressively throughout the project risk management process . thresults of perform qualitative risk analysis , perform quantitative risk analysis , plan risk response , implement risresponses , and monitor risk be also include in the risk report a those process be complete . on completion the identify risk process , information in the risk report may include but be not limit to : summary information on identified individual project risk , such a number of identified threat and opportunitielistribution of risk across risk category , metric and trend , etc .
37 | 11.2.3.3 project documents updates | @ assumption log. described in section 4.1.3.2. during the identify risks process, new assumptions may be made, new constraints may be identified, and existing assumptions or constraints may be revisited and changed. the assumption log should be updated with this new information. @ lessons learned register. described in section 4.4.3.1. the lessons learned register can be updated with information on techniques that were effective in identifying risks to improve performance in later phases or other projects. | assumption log . describe in section 4.1.3.2. during the identify risk process , new assumption may bemade , new constraint may be identify , and exist assumption or constraint may be revisit and changed.the assumption log should be update with this new information . lesson learn register . describe in section 4.4.3.1. the lesson learn register can be update withinformation on technique that be effective in identify risk to improve performance in late phase orother project .
38 | 11.3 perform qualitative risk analysis | perform qualitative risk analysis is the process of prioritizing individual project risks for further analysis or action by assessing their probability of occurrence and impact as well as other characteristics. the key benefit of this process is that it focuses efforts on high-priority risks. this process is performed throughout the project. the inputs, tools and techniques, and outputs of the process are depicted in figure 11-8. figure 11-9 depicts the data flow diaoram for the process. figure 11-8. perform qualitative risk analysis: inputs, tools & techniques, and outputs Figure 11-9. Perform Qualitative Risk Analysis: Data Flow Diagram Perform Qualitative Risk Analysis assesses the priority of identified individual project risks using their probability of occurrence, the corresponding impact on project objectives if the risks occur, and other factors. Such assessments are subjective as they are based on perceptions of risk by the project team and other stakeholders. Effective assessment therefore requires explicit identification and management of the risk attitudes of key participants in the Perform Qualitative Risk Analysis process. Risk perception introduces bias into the assessment of identified risks, so attention should be paid to identifying bias and correcting for it. Where a facilitator is used to support the Perform Qualitative Risk Analysis process, addressing bias is a key part of the facilitator’s role. An evaluation of the quality of the available information on individual project risks also helps to clarify the assessment of each risk’s importance to the project. Perform Qualitative Risk Analysis establishes the relative priorities of individual project risks for Plan Risk Responses. t identifies a risk owner for each risk who will take responsibility for planning an appropriate risk response and ensuring hat it is implemented. Perform Qualitative Risk Analysis also lays the foundation for Perform Quantitative Risk Analysis f this process is required. The Perform Qualitative Risk Analysis process is performed regularly throughout the project life cycle, as defined in the risk management plan. Often, in an agile development environment, the Perform Qualitative Risk Analysis process is conducted before the start of each iteration. | perform qualitative risk analysis be the process of prioritize individual project risk for further analysis or actionby assess their probability of occurrence and impact as well a other characteristic . the key benefit of thisprocess be that it focus effort on high-priority risk . this process be perform throughout the project . the input , tool and technique , and output of the process be depict in figure 11-8. figure 11-9 depict the data flowdiaoram for the process.figure 11-8. perform qualitative risk analysis : input , tool & technique , and outputsfigure 11-9 . perform qualitative risk analysis : data flow diagramperform qualitative risk analysis assess the priority of identified individual project risk use their probability ofoccurrence , the corresponding impact on project objective if the risk occur , and other factor . such assessment aresubjective a they be base on perception of risk by the project team and other stakeholder . effective assessmenttherefore require explicit identification and management of the risk attitude of key participant in the performqualitative risk analysis process . risk perception introduces bias into the assessment of identified risk , so attentionshould be pay to identify bias and correct for it . where a facilitator be use to support the perform qualitativerisk analysis process , address bias be a key part of the facilitator ’ s role . an evaluation of the quality of the availableinformation on individual project risk also help to clarify the assessment of each risk ’ s importance to the project.perform qualitative risk analysis establish the relative priority of individual project risk for plan risk responses.t identify a risk owner for each risk who will take responsibility for plan an appropriate risk response and ensuringhat it be implement . perform qualitative risk analysis also lay the foundation for perform quantitative risk analysisf this process be required.the perform qualitative risk analysis process be perform regularly throughout the project life cycle , a define inthe risk management plan . often , in an agile development environment , the perform qualitative risk analysis process isconducted before the start of each iteration .
39 | 11.3.1 perform qualitative risk analysis: inputs
40 | 11.3.1.1 project management plan | described in section 4.2.3.1. project management plan components include the risk management plan as described in section 11.1.3.1. of particular interest in this process are the roles and responsibilities for conducting risk management, budgets for risk management, schedule activities for risk management, risk categories (often defined ir a risk breakdown structure), definitions of probability and impact, the probability and impact matrix, and stakeholders risk thresholds. these inputs are usually tailored to the project during the plan risk management process. if they are not available, they may be developed during the perform qualitative risk analysis process and presented to the project sponsor for approval before use. | describe in section 4.2.3.1. project management plan component include the risk management plan asdescribed in section 11.1.3.1. of particular interest in this process be the role and responsibility for conduct riskmanagement , budget for risk management , schedule activity for risk management , risk category ( often define ira risk breakdown structure ) , definition of probability and impact , the probability and impact matrix , and stakeholdersrisk threshold . these input be usually tailor to the project during the plan risk management process . if they arenot available , they may be develop during the perform qualitative risk analysis process and present to the projectsponsor for approval before use .
41 | 11.3.1.2 project documents | @ assumption log. described in section 4.1.3.2. the assumption log is used for identifying, managing, and monitoring key assumptions and constraints that may affect the project. these may inform the assessment of the priority of individual project risks. @ risk register. described in section 11.2.3.1. the risk register contains details of each identified individual project risk that will be assessed during the perform qualitative risk analysis process. @ chalnahaldave vraniactare nnaanariknd in cantinn 194904 thie inalidan aantaile anf nrninnat atal-nhanldare ushn mais hn | assumption log . describe in section 4.1.3.2. the assumption log be use for identify , managing , andmonitoring key assumption and constraint that may affect the project . these may inform the assessment ofthe priority of individual project risk . risk register . describe in section 11.2.3.1. the risk register contain detail of each identify individual projectrisk that will be assess during the perform qualitative risk analysis process . chalnahaldave vraniactare nnaanariknd in cantinn 194904 thie inalidan aantaile anf nrninnat atal-nhanldare ushn mais hn
42 | 11.3.1.3 enterprise environmental factors | 11.3.1.3 enterprise environmental factors the enterprise environmental factors that can influence perform qualitative risk analysis include but are not limited to: @ industry studies of similar projects, and the enterprise environmental factors that can influence perform qualitative risk analysis include but are not limited to: @ published material, including commercial risk databases or checklists. | 11.3.1.3 enterprise environmental factorsthe enterprise environmental factor that can influence perform qualitative risk analysis include but be not limit to : industry study of similar project , andthe enterprise environmental factor that can influence perform qualitative risk analysis include but be not limit to : publish material , include commercial risk database or checklist .
43 | 11.3.1.4 organizational process assets
44 | 11.3.2 perform qualitative risk analysis: tools and techniques
45 | 11.3.2 perform qualitative risk analysis: tools a
46 | 11.3.2.1 expert judgment | pi.j.2.) capemne judunieine described in section 4.1.2.1. expertise should be considered from individuals or groups with specialized knowledge or training in the following topics: expert judgment is often obtained through facilitated risk workshops or interviews. the possibility of expert views being biased should be taken into account in this process. | pi.j.2 . ) capemne judunieinedescribed in section 4.1.2.1. expertise should be consider from individual or group with specialized knowledgeor training in the following topic : expert judgment be often obtain through facilitate risk workshop or interview . the possibility of expert viewsbeing bias should be take into account in this process .
47 | 11.3.2.2 data gathering | data-gathering techniques that can be used for this process include but are not limited to interviews. structured or semi-structured interviews (section 5.2.2.2) can be used to assess the probability and impacts of individual project risks, as well as other factors. the interviewer should promote an environment of trust and confidentiality in the interview setting to encourage honest and unbiased assessments. | data-gathering technique that can be use for this process include but be not limit to interview . structure orsemi-structured interview ( section 5.2.2.2 ) can be use to assess the probability and impact of individual project risk , as well a other factor . the interviewer should promote an environment of trust and confidentiality in the interviewsetting to encourage honest and unbiased assessment .
48 | 11.3.2.3 data analysis | data analysis techniques that can be used during this process include but are not limited to: @ risk data quality assessment. risk data quality assessment evaluates the degree to which the data about individual project risks is accurate and reliable as a basis for qualitative risk analysis. the use of low-quality risk data may lead to a qualitative risk analysis that is of little use to the project. if data quality is unacceptable, it may be necessary to gather better data. risk data quality may be assessed via a questionnaire measuring the project's stakeholder perceptions of various characteristics, which may include completeness, objectivity, relevancy, and timeliness. a weighted average of selected data quality characteristics can then be generated to give an overall quality score. ees sst ce lg relevancy, and timeliness. a weighted a average of selected data quality characteristics can 1 then be generated to give an overall quality score. @ risk probability and impact assessment. risk probability assessment considers the likelihood that a specific risk will occur. risk impact assessment considers the potential effect on one or more project objectives such as schedule, cost, quality, or performance. impacts will be negative for threats and positive for opportunities. probability and impact are assessed for each identified individual project risk. risks can be assessed in interviews or meetings with participants selected for their familiarity with the types of risk recorded in the risk register. project team members and knowledgeable persons external to the project are included. the level of probability for each risk and its impact on each objective are evaluated during the interview or meeting. differences in the levels of probability and impact perceived by stakeholders are to be expected, and such differences should be explored. explanatory detail, including assumptions justifying the levels assigned, are also recorded. risk probabilities and impacts are assessed using the definitions given in the risk management plan (see table 11-1). risks with low probability and impact may be included within the risk register as part of a watch list for future monitoring. @ assessment of other risk parameters. the project team may consider other characteristics of risk (in addition @ assessment of other risk parameters. the project team may consider other characteristics of risk (in addition to probability and impact) when prioritizing individual project risks for further analysis and action. these characteristics may include but are not limited to: Urgency. The period of time within which a response to the risk is to be implemented in order to be effective. A short period indicates high urgency. Proximity. The period of time before the risk might have an impact on one or more project objectives. A short period indicates high proximity. Dormancy. The period of time that may elapse after a risk has occurred before its impact is discovered. A short period indicates low dormancy. Manageability. The ease with which the risk owner (or owning organization) can manage the occurrence or impact of a risk. Where management is easy, manageability is high. Controllability. The degree to which the risk owner (or owning organization) is able to control the risk’s outcome. Where the outcome can be easily controlled, controllability is high. Detectability. The ease with which the results of the risk occurring, or being about to occur, can be detected and recognized. Where the risk occurrence can be detected easily, detectability is high. Connectivity. The extent to which the risk is related to other individual project risks. Where a risk is connected to many other risks, connectivity is high. Strategic impact. The potential for the risk to have a positive or negative effect on the organization’s strategic goals. Where the risk has a major effect on strategic goals, strategic impact is high. Propinquity. The degree to which a risk is perceived to matter by one or more stakeholders. Where a risk is perceived as very significant, propinquity is high. | data analysis technique that can be use during this process include but be not limit to : risk data quality assessment . risk data quality assessment evaluate the degree to which the data aboutindividual project risk be accurate and reliable a a basis for qualitative risk analysis . the use of low-qualityrisk data may lead to a qualitative risk analysis that be of little use to the project . if data quality be unacceptable , it may be necessary to gather good data . risk data quality may be assess via a questionnaire measuringthe project 's stakeholder perception of various characteristic , which may include completeness , objectivity , relevancy , and timeliness . a weighted average of select data quality characteristic can then be generate togive an overall quality score . ee sst ce lgrelevancy , and timeliness . a weight a average of select data quality characteristic can 1 then be generate togive an overall quality score . risk probability and impact assessment . risk probability assessment consider the likelihood that a specificrisk will occur . risk impact assessment consider the potential effect on one or more project objectives suchas schedule , cost , quality , or performance . impact will be negative for threat and positive for opportunities.probability and impact be assess for each identify individual project risk . risk can be assess ininterviews or meeting with participant select for their familiarity with the type of risk record in therisk register . project team member and knowledgeable person external to the project be include . the levelof probability for each risk and it impact on each objective be evaluate during the interview or meeting.differences in the level of probability and impact perceive by stakeholder be to be expect , and suchdifferences should be explore . explanatory detail , include assumption justify the level assign , arealso record . risk probability and impact be assess use the definition give in the risk managementplan ( see table 11-1 ) . risk with low probability and impact may be include within the risk register a partof a watch list for future monitoring . assessment of other risk parameter . the project team may consider other characteristic of risk ( in addition assessment of other risk parameter . the project team may consider other characteristic of risk ( in additionto probability and impact ) when prioritize individual project risk for further analysis and action . thesecharacteristics may include but be not limit to : urgency . the period of time within which a response to the risk be to be implement in order to be effective.a short period indicate high urgency.proximity . the period of time before the risk might have an impact on one or more project objective . a shortperiod indicate high proximity.dormancy . the period of time that may elapse after a risk have occur before it impact be discover . ashort period indicate low dormancy.manageability . the ease with which the risk owner ( or own organization ) can manage the occurrence orimpact of a risk . where management be easy , manageability be high.controllability . the degree to which the risk owner ( or own organization ) be able to control the risk ’ soutcome . where the outcome can be easily control , controllability be high.detectability . the ease with which the result of the risk occurring , or be about to occur , can be detectedand recognize . where the risk occurrence can be detect easily , detectability be high.connectivity . the extent to which the risk be relate to other individual project risk . where a risk be connectedto many other risk , connectivity be high.strategic impact . the potential for the risk to have a positive or negative effect on the organization ’ s strategicgoals . where the risk have a major effect on strategic goal , strategic impact be high.propinquity . the degree to which a risk be perceive to matter by one or more stakeholder . where a risk isperceived a very significant , propinquity be high .
49 | 11.3.2.4 interpersonal and team skills | interpersonal and team skills that can be used for this process include but are not limited to facilitation (see section 4.1.2.3). facilitation improves the effectiveness of the qualitative analysis of individual project risks. a skilled facilitator can help participants remain focused on the risk analysis task, follow the method associated with the technique accurately, reach consensus on assessments of probability and impacts, identify and overcome sources of bias, and resolve any disagreements that may arise. | interpersonal and team skill that can be use for this process include but be not limit to facilitation ( see section4.1.2.3 ) . facilitation improve the effectiveness of the qualitative analysis of individual project risk . a skilled facilitatorcan help participant remain focused on the risk analysis task , follow the method associate with the techniqueaccurately , reach consensus on assessment of probability and impact , identify and overcome source of bias , andresolve any disagreement that may arise .
50 | 11.3.2.5 risk categorization | risks to the project can be categorized by sources of risk (e.g., using the risk breakdown structure (rbs); see figure 11-4), the area of the project affected (e.g., using the work breakdown structure (wbs); see figures 5-12, 5-13, and 5-14), or other useful categories (e.g., project phase, project budget, and roles and responsibilities) to determine the areas of the project most exposed to the effects of uncertainty. risks can also be categorized by common root causes. risk categories that may be used for the project are defined in the risk management plan. | risk to the project can be categorize by source of risk ( e.g. , use the risk breakdown structure ( rbs ) ; seefigure 11-4 ) , the area of the project affect ( e.g. , use the work breakdown structure ( wbs ) ; see figure 5-12,5-13 , and 5-14 ) , or other useful category ( e.g. , project phase , project budget , and role and responsibility ) todetermine the area of the project most expose to the effect of uncertainty . risk can also be categorize bycommon root cause . risk category that may be use for the project be define in the risk management plan .
51 | 11.3.2.6 data representation | vala igvicocinauutt louinnyugs uldl udll ug uotu uulitty ullo viuugoo higligug mul aio tul titou lu. @ probability and impact matrix. a probability and impact matrix is a grid for mapping the probability of eac! risk occurrence and its impact on project objectives if that risk occurs. this matrix specifies combinations o probability and impact that allow individual project risks to be divided into priority groups (see figure 11-5). risk: can be prioritized for further analysis and planning of risk responses based on their probability and impacts the probability of occurrence for each individual project risk is assessed as well as its impact on one or mor project objectives if it does occur, using definitions of probability and impact for the project as specified in the risk management plan. individual project risks are assigned to a priority level based on the combination of thei assessed probability and impact, using a probability and impact matrix. an organization can assess a risk separately for each objective (e.g., cost, time, and scope) by having a separate probability and impact matrix for each. alternatively, it may develop ways to determine one overall priority level for each risk, either by combining assessments for different objectives, or by taking the highest priority level regardless of which objective is affected. @ hierarchical charts. where risks have been categorized using more than two parameters, the probability anc impact matrix cannot be used and other graphical representations are required. for example, a bubble chart displays three dimensions of data, where each risk is plotted as a disk (bubble), and the three parameters are representec by the x-axis value, the y-axis value, and the bubble size. an example bubble chart is shown in figure 11-10, witt detectability and proximity plotted on the x and y axes, and impact value represented by bubble size. Figure 11-10. Example Bubble Chart Showing Detectability, Proximity, and Impact Value | vala igvicocinauutt louinnyugs uldl udll ug uotu uulitty ullo viuugoo higligug mul aio tul titou lu . probability and impact matrix . a probability and impact matrix be a grid for map the probability of eac ! risk occurrence and it impact on project objective if that risk occur . this matrix specifies combination oprobability and impact that allow individual project risk to be divide into priority group ( see figure 11-5 ) . risk : can be prioritize for further analysis and planning of risk response base on their probability and impactsthe probability of occurrence for each individual project risk be assess as well a it impact on one or morproject objective if it do occur , use definition of probability and impact for the project a specify in therisk management plan . individual project risk be assign to a priority level base on the combination of theiassessed probability and impact , use a probability and impact matrix.an organization can assess a risk separately for each objective ( e.g. , cost , time , and scope ) by have a separateprobability and impact matrix for each . alternatively , it may develop way to determine one overall priority levelfor each risk , either by combine assessment for different objective , or by take the high priority levelregardless of which objective be affect . hierarchical chart . where risk have be categorize use more than two parameter , the probability ancimpact matrix can not be use and other graphical representation be require . for example , a bubble chart displaysthree dimension of data , where each risk be plot a a disk ( bubble ) , and the three parameter be representecby the x-axis value , the y-axis value , and the bubble size . an example bubble chart be show in figure 11-10 , wittdetectability and proximity plot on the x and y ax , and impact value represent by bubble size.figure 11-10 . example bubble chart show detectability , proximity , and impact value
52 | 11.3.2.7 meetings | to undertake qualitative risk analysis, the project team may conduct a specialized meeting (often called a risk workshop) dedicated to the discussion of identified individual project risks. the goals of this meeting include the review of previously identified risks, assessment of probability and impacts (and possibly other risk parameters), categorization, and prioritization. a risk owner, who will be responsible for planning an appropriate risk response and for reporting progress on managing the risk, will be allocated to each individual project risk as part of the perform qualitative risk analysis process. the meeting may start by reviewing and confirming the probability and impact scales to be used for the analysis. the meeting may also identify additional risks during the discussion, and these should be recorded for analysis. use of a skilled facilitator will increase the effectiveness of the meeting. | to undertake qualitative risk analysis , the project team may conduct a specialized meeting ( often call a riskworkshop ) dedicate to the discussion of identified individual project risk . the goal of this meeting include the reviewof previously identify risk , assessment of probability and impact ( and possibly other risk parameter ) , categorization , and prioritization . a risk owner , who will be responsible for plan an appropriate risk response and for reportingprogress on manage the risk , will be allocate to each individual project risk a part of the perform qualitative riskanalysis process . the meeting may start by review and confirm the probability and impact scale to be use forthe analysis . the meeting may also identify additional risk during the discussion , and these should be record foranalysis . use of a skilled facilitator will increase the effectiveness of the meeting .
53 | 11.3.3 perform qualitative risk analysis: outputs
54 | 11.3.3.1 project documents updates | @ assumption log. described in section 4.1.3.2. during the perform qualitative risk analysis process, new assumptions may be made, new constraints may be identified, and existing assumptions or constraints may be revisited and changed. the assumption log should be updated with this new information. @ risk register. described in section 11.2.3.1. the risk register is updated with new information generated during the perform qualitative risk analysis process. updates to the risk register may include assessments of probability and impacts for each individual project risk, its priority level or risk score, the nominated risk owner, risk urgency information or risk categorization, and a watch list for low-priority risks or risks requiring further analysis. @ risk report. described in section 11.2.3.2. the risk report is updated to reflect the most important individual project risks (usually those with the highest probability and impact), as well as a prioritized list of all identified risks on the project and a summary conclusion. | assumption log . describe in section 4.1.3.2. during the perform qualitative risk analysis process , newassumptions may be make , new constraint may be identify , and exist assumption or constraint may berevisited and change . the assumption log should be update with this new information . risk register . describe in section 11.2.3.1. the risk register be update with new information generate duringthe perform qualitative risk analysis process . update to the risk register may include assessment of probabilityand impact for each individual project risk , it priority level or risk score , the nominated risk owner , risk urgencyinformation or risk categorization , and a watch list for low-priority risk or risk require further analysis . risk report . describe in section 11.2.3.2. the risk report be update to reflect the most important individualproject risk ( usually those with the high probability and impact ) , as well a a prioritized list of all identifiedrisks on the project and a summary conclusion .
55 | 11.4 perform quantitative risk analysis | perform quantitative risk analysis is the process of numerically analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives. the key benefit of this process is that it quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning. this process is not required for every project, but where it is used, it is performed throughout the project. the inputs and outputs of this process are depicted in figure 11-11. figure 11-12 depicts the data flow diagram for the process. figure 11-11. perform quantitative risk analysis: inputs, tools & techniques, and outputs Figure 11-12. Perform Quantitative Risk Analysis: Data Flow Diagram Perform Quantitative Risk Analysis is not required for all projects. Undertaking a robust analysis depends on the availability of high-quality data about individual project risks and other sources of uncertainty, as well as a sound underlying project baseline for scope, schedule, and cost. Quantitative risk analysis usually requires specialized risk software and expertise in the development and interpretation of risk models. It also consumes additional time and cost. The use of quantitative risk analysis for a project will be specified in the project’s risk management plan. It is most likely appropriate for large or complex projects, strategically important projects, projects for which it is a contractual requirement, or projects in which a key stakeholder requires it. Quantitative risk analysis is the only reliable method to assess overall project risk through evaluating the aggregated effect on project outcomes of all individual project risks and other sources of uncertainty. Outputs from Perform Quantitative Risk Analysis are used as inputs to the Plan Risk Responses process, particularly in recommending responses to the level of overall project risk and key individual risks. A quantitative risk analysis may also be undertaken following the Plan Risk Responses process, to determine the likely effectiveness of planned responses in reducing overall project risk exposure. | perform quantitative risk analysis be the process of numerically analyze the combined effect of identified individualproject risk and other source of uncertainty on overall project objective . the key benefit of this process be that itquantifies overall project risk exposure , and it can also provide additional quantitative risk information to support riskresponse planning . this process be not require for every project , but where it be use , it be perform throughout theproject . the input and output of this process be depict in figure 11-11. figure 11-12 depict the data flow diagramfor the process.figure 11-11. perform quantitative risk analysis : input , tool & technique , and outputsfigure 11-12 . perform quantitative risk analysis : data flow diagramperform quantitative risk analysis be not require for all project . undertake a robust analysis depend on the availabilityof high-quality data about individual project risk and other source of uncertainty , as well a a sound underlying projectbaseline for scope , schedule , and cost . quantitative risk analysis usually require specialized risk software and expertisein the development and interpretation of risk model . it also consume additional time and cost . the use of quantitativerisk analysis for a project will be specify in the project ’ s risk management plan . it be most likely appropriate for large orcomplex project , strategically important project , project for which it be a contractual requirement , or project in whicha key stakeholder require it . quantitative risk analysis be the only reliable method to assess overall project risk throughevaluating the aggregated effect on project outcome of all individual project risk and other source of uncertainty.outputs from perform quantitative risk analysis be use a input to the plan risk response process , particularlyin recommend response to the level of overall project risk and key individual risk . a quantitative risk analysismay also be undertake follow the plan risk response process , to determine the likely effectiveness of plannedresponses in reduce overall project risk exposure .
56 | 11.4.1 perform quantitative risk analysis: input
57 | 11.4.1.1 project management plan | described in section 4.2.3.1. project management plan components include but are not limited to: @ risk management plan. described in section 11.1.3.1. the risk management plan specifies whether quantitative risk analysis is required for the project. it also details the resources available for the analysis and the expected frequency of analyses. schedule baseline. described in section 6.5.3.1. the schedule baseline describes the starting point from whic! the effect of individual project risks and other sources of uncertainty can be evaluated. @ cost baseline. described in section 7.3.3.1. the cost baseline describes the starting point from ¦ of individual project risks and other sources of uncertainty can be evaluated. | describe in section 4.2.3.1. project management plan component include but be not limit to : risk management plan . describe in section 11.1.3.1. the risk management plan specify whether quantitativerisk analysis be require for the project . it also detail the resource available for the analysis and the expectedfrequency of analyses.schedule baseline . describe in section 6.5.3.1. the schedule baseline describe the start point from whic ! the effect of individual project risk and other source of uncertainty can be evaluate . cost baseline . describe in section 7.3.3.1. the cost baseline describe the start point from ¦of individual project risk and other source of uncertainty can be evaluate .
58 | 11.4.1.2 project documents | @ assumption log. described in section 4.1.3.2. assumptions may form inputs to the quantitative risk analysis if they are assessed as posing a risk to project objectives. the effect of constraints may also be modeled during a quantitative risk analysis. @ basis of estimates. described in sections 6.4.3.2 and 7.2.3.2. the basis of estimates used in the planning of the project may be reflected in variability modeled during a quantitative risk analysis process. this may include information on the estimate’s purpose, classification, assumed accuracy, methodology, and source. @ cost estimates. described in section 7.2.3.1. cost estimates provide the starting point from which cost variability is evaluated. @ cost forecasts. described in section 7.4.3.2. forecasts such as the project’s estimate to complete (etc), estimate at completion (eac), budget at completion (bac), and to-complete performance index (tcpi) may be compared to the results of a quantitative cost risk analysis to determine the confidence level associated with achieving these targets. > duration estimates. described in section 6.4.3.1. duration estimates provide the starting point from whic schedule variability is evaluated. @ milestone list. described in section 6.2.3.3. significant events in the project define the schedule targets against which the results of a quantitative schedule risk analysis are compared, in order to determine the confidence level associated with achieving these targets. @ Resource requirements. Described in Section 9.2.3.1. Resource requirements provide the starting point from which variability is evaluated. @ Schedule forecasts. Described in Section 6.6.3.2. Forecasts may be compared to the results of a quantitative schedule risk analysis to determine the confidence level associated with achieving these targets. | assumption log . describe in section 4.1.3.2. assumption may form input to the quantitative risk analysis ifthey be assess a pose a risk to project objective . the effect of constraint may also be model during aquantitative risk analysis . basis of estimate . describe in section 6.4.3.2 and 7.2.3.2. the basis of estimate use in the planning ofthe project may be reflect in variability model during a quantitative risk analysis process . this may includeinformation on the estimate ’ s purpose , classification , assume accuracy , methodology , and source . cost estimate . describe in section 7.2.3.1. cost estimate provide the start point from which cost variabilityis evaluate . cost forecast . describe in section 7.4.3.2. forecast such a the project ’ s estimate to complete ( etc ) , estimate at completion ( eac ) , budget at completion ( bac ) , and to-complete performance index ( tcpi ) may becompared to the result of a quantitative cost risk analysis to determine the confidence level associate withachieving these targets. > duration estimate . describe in section 6.4.3.1. duration estimate provide the start point from whicschedule variability be evaluate . milestone list . describe in section 6.2.3.3. significant event in the project define the schedule target againstwhich the result of a quantitative schedule risk analysis be compare , in order to determine the confidencelevel associate with achieve these target . resource requirement . describe in section 9.2.3.1 . resource requirement provide the starting point fromwhich variability be evaluate . schedule forecast . describe in section 6.6.3.2 . forecast may be compare to the result of a quantitativeschedule risk analysis to determine the confidence level associate with achieve these target .
59 | 11.4.1.3 enterprise environmental factors | @ published material, including commercial risk databases or checklist | publish material , include commercial risk database or checklist
60 | 11.4.1.4 organizational process assets
61 | 11.4.2 perform quantitative risk analysis: tools and techniques
62 | 11.4.2.1 expert judgment | piet.2.) lap eee vuduniline described in section 4.1.2.1. expertise should be considered from individuals or groups with specialized knowledge or training in the following topics: translating information on individual project risks and other sources of uncertainty into numeric inputs for the niantitative rick analyeie mndaol quantitative risk analysis model, @ selecting the most appropriate representation of uncertain @ modeling techniques that are appropriate in the context @ identifying which tools would be most suitable for the se @ interpreting the outputs of quantitative risk analysis. | piet.2 . ) lap eee vudunilinedescribed in section 4.1.2.1. expertise should be consider from individual or group with specialized knowledgeor training in the following topic : translate information on individual project risk and other source of uncertainty into numeric input for theniantitative rick analyeie mndaolquantitative risk analysis model , select the most appropriate representation of uncertain model technique that be appropriate in the context identifying which tool would be most suitable for the se interpret the output of quantitative risk analysis .
63 | 11.4.2.2 data gathering | interviews (see section 5.2.2.2) may be used to generate inputs for the quantitative risk analysis, drawing on inputs that include individual project risks and other sources of uncertainty. this is particularly useful where information is required from experts. the interviewer should promote an environment of trust and confidentiality during the interview to encourage honest and unbiased contributions. | interview ( see section 5.2.2.2 ) may be use to generate input for the quantitative risk analysis , draw on inputsthat include individual project risk and other source of uncertainty . this be particularly useful where information isrequired from expert . the interviewer should promote an environment of trust and confidentiality during the interviewto encourage honest and unbiased contribution .
64 | 11.4.2.3 interpersonal and team skills | interpersonal and team skills that can be used for this process include but are not limited to facilitation (see section 4.1.2.3). a skilled facilitator is useful for gathering input data during a dedicated risk workshop involving project team members and other stakeholders. facilitated workshops can improve effectiveness by establishing a clear understanding of the purpose of the workshop, building consensus among participants, ensuring continued focus on the task, and using creative approaches to deal with interpersonal conflict or sources of bias. | interpersonal and team skill that can be use for this process include but be not limit to facilitation ( seesection 4.1.2.3 ) . a skilled facilitator be useful for gather input data during a dedicate risk workshop involvingproject team member and other stakeholder . facilitate workshop can improve effectiveness by establish aclear understanding of the purpose of the workshop , build consensus among participant , ensure continuedfocus on the task , and use creative approach to deal with interpersonal conflict or source of bias .
65 | 11.4.2.4 representations of uncertainty | quantitative risk analysis requires inputs to a quantitative risk analysis model that reflect individual project risks and ther sources of uncertainty. where the duration, cost, or resource requirement for a planned activity is uncertain, the range of possible values can be represented in the model as a probability distribution. this may take several forms. the most commonly used are triangular, normal, lognormal, beta, uniform, or discrete distributions. care should be taken when selecting an appropriate probability distribution to reflect the range of possible values for the planned activity. individual project risks may be covered by probability distributions. alternatively, risks may be included in the model as probabilistic branches, where optional activities are added to the model to represent the time and/or cost impact of the risk should it occur, and the chance that these activities actually occur in a particular simulation run matches the risk’s probability. branches are most useful for risks that might occur independently of any planned activity. where risks are related, for example, with a common cause or a logical dependency, correlation is used in the model to indicate this relationship. | quantitative risk analysis require input to a quantitative risk analysis model that reflect individual project risk andther source of uncertainty.where the duration , cost , or resource requirement for a planned activity be uncertain , the range of possible valuescan be represent in the model a a probability distribution . this may take several form . the most commonly usedare triangular , normal , lognormal , beta , uniform , or discrete distribution . care should be take when select anappropriate probability distribution to reflect the range of possible value for the planned activity.individual project risk may be cover by probability distribution . alternatively , risk may be include in themodel a probabilistic branch , where optional activity be add to the model to represent the time and/or costimpact of the risk should it occur , and the chance that these activity actually occur in a particular simulation runmatches the risk ’ s probability . branch be most useful for risk that might occur independently of any plannedactivity . where risk be relate , for example , with a common cause or a logical dependency , correlation be use inthe model to indicate this relationship .
66 | 11.4.2.5 data analysis | data analysis techniques that can be used during this process include but are not limited to: @ simulation. quantitative risk analysis uses a model that simulates the combined effects of individual project risks and other sources of uncertainty to evaluate their potential impact on achieving project objectives. simulation: are typically performed using a monte carlo analysis. when running a monte carlo analysis for cost risk, the simulation uses the project cost estimates. when running a monte carlo analysis for schedule risk, the schedule network diagram and duration estimates are used. an integrated quantitative cost-schedule risk analysis use: both inputs. the output is a quantitative risk analysis model. computer software is used to iterate the quantitative risk analysis model several thousand times. the input values (e.g., cost estimates, duration estimates, or occurrence of probabilistic branches) are chosen at random for each iteration. outputs represent the range of possible outcomes for the project (e.g., project end date, project cost at completion). typical outputs include a histogram presenting the number of iterations where a particular outcome resulted from the simulation, or a cumulative probability distribution (s-curve) representing the probability of achieving any particular outcome or less. an example s-curve from a monte carlo cost risk analysis is shown in figure 11-13. figure 11-13. example s-curve from quantitative cost risk analysis For a quantitative schedule risk analysis, it is also possible to conduct a criticality analysis that determines which elements of the risk model have the greatest effect on the project critical path. A criticality index is calculated for each element in the risk model, which gives the frequency with which that element appears on the critical path during the simulation, usually expressed as a percentage. The output from a criticality analysis allows the project team to focus risk response planning efforts on those activities with the highest potential effect on the overall schedule performance of the project. @ Sensitivity analysis. Sensitivity analysis helps to determine which individual project risks or other sources of uncertainty have the most potential impact on project outcomes. It correlates variations in project outcomes with variations in elements of the quantitative risk analysis model. One typical display of sensitivity analysis is the tornado diagram, which presents the calculated correlation coefficient for each element of the quantitative risk analysis model that can influence the project outcome. This can include individual project risks, project activities with high degrees of variability, or specific sources of ambiguity. Items are ordered by descending strength of correlation, giving the typical tornado appearance. An example tornado diagram is shown in Figure 11-14. Figure 11-14. Example Tornado Diagram @ Decision tree analysis. Decision trees are used to support selection of the best of several alternative courses 0 action. Alternative paths through the project are shown in the decision tree using branches representing differen decisions or events, each of which can have associated costs and related individual project risks (including bott threats and opportunities). The end-points of branches in the decision tree represent the outcome from followin that particular path, which can be negative or positive. Figure 11-15. Example Decision Tree @ Influence diagrams. Influence diagrams are graphical aids to decision making under uncertainty. An influence diagram represents a project or situation within the project as a set of entities, outcomes, and influences, together with the relationships and effects between them. Where an element in the influence diagram is uncertain as a result of the existence of individual project risks or other sources of uncertainty, this can be represented in the influence diagram using ranges or probability distributions. The influence diagram is then evaluated using a simulation technique, such as Monte Carlo analysis, to indicate which elements have the greatest influence on key outcomes. Outputs from an influence diagram are similar to other quantitative risk analysis methods, including S-curves and tornado diagrams. | data analysis technique that can be use during this process include but be not limit to : simulation . quantitative risk analysis use a model that simulate the combined effect of individual project risksand other source of uncertainty to evaluate their potential impact on achieve project objective . simulation : be typically perform use a monte carlo analysis . when run a monte carlo analysis for cost risk , thesimulation use the project cost estimate . when run a monte carlo analysis for schedule risk , the schedulenetwork diagram and duration estimate be use . an integrated quantitative cost-schedule risk analysis use : both input . the output be a quantitative risk analysis model.computer software be use to iterate the quantitative risk analysis model several thousand time . the inputvalues ( e.g. , cost estimate , duration estimate , or occurrence of probabilistic branch ) be choose at randomfor each iteration . output represent the range of possible outcome for the project ( e.g. , project end date , project cost at completion ) . typical output include a histogram present the number of iteration where aparticular outcome result from the simulation , or a cumulative probability distribution ( s-curve ) representingthe probability of achieve any particular outcome or less . an example s-curve from a monte carlo cost riskanalysis be show in figure 11-13.figure 11-13. example s-curve from quantitative cost risk analysisfor a quantitative schedule risk analysis , it be also possible to conduct a criticality analysis that determine whichelements of the risk model have the great effect on the project critical path . a criticality index be calculate foreach element in the risk model , which give the frequency with which that element appear on the critical pathduring the simulation , usually express a a percentage . the output from a criticality analysis allow the projectteam to focus risk response plan effort on those activity with the high potential effect on the overallschedule performance of the project . sensitivity analysis . sensitivity analysis help to determine which individual project risk or other source ofuncertainty have the most potential impact on project outcome . it correlate variation in project outcome withvariations in element of the quantitative risk analysis model.one typical display of sensitivity analysis be the tornado diagram , which present the calculated correlationcoefficient for each element of the quantitative risk analysis model that can influence the project outcome.this can include individual project risk , project activity with high degree of variability , or specific sourcesof ambiguity . item be order by descend strength of correlation , give the typical tornado appearance.an example tornado diagram be show in figure 11-14.figure 11-14 . example tornado diagram decision tree analysis . decision tree be use to support selection of the best of several alternative course 0action . alternative path through the project be show in the decision tree use branch represent differendecisions or event , each of which can have associate cost and related individual project risk ( include bottthreats and opportunity ) . the end-points of branch in the decision tree represent the outcome from followinthat particular path , which can be negative or positive.figure 11-15 . example decision tree influence diagram . influence diagram be graphical aid to decision make under uncertainty . an influencediagram represent a project or situation within the project a a set of entity , outcome , and influence , togetherwith the relationship and effect between them . where an element in the influence diagram be uncertain a aresult of the existence of individual project risk or other source of uncertainty , this can be represent in theinfluence diagram use range or probability distribution . the influence diagram be then evaluate use asimulation technique , such a monte carlo analysis , to indicate which element have the great influenceon key outcome . output from an influence diagram be similar to other quantitative risk analysis method , include s-curves and tornado diagram .
67 | 11.4.3 perform quantitative risk analysis: outputs
68 | 11.4.3.1 project documents updates | project documents that can be considered as outputs for this process include but are not limited to the risk report described in section 11.2.3.2. the risk report will be updated to reflect the results of the quantitative risk analysis. this will typically include: m chances of project success, indicated by the probability that the project will achieve its key objectives (e.g., required end date or interim milestones, required cost target, etc.) given the identified individual project risks and other sources of uncertainty; and @ detailed probabilistic analysis of the project. key outputs from the quantitative risk analysis are present such as s-curves, tornado diagrams, and criticality analysis, together with a narrative interpretation of the resu possible detailed results of a quantitative risk analysis may include: m= amount of contingency reserve needed to provide a specified level of confidence; = identification of individual project risks or other sources of uncertainty that have the greatest effect o project critical path; and m= major drivers of overall project risk, with the greatest influence on uncertainty in project outcomes. @ trends in quantitative risk analysis results. as the analysis is repeated at different times during the projec cycle, trends may become apparent that inform the planning of risk responses. @ recommended risk responses. the risk report may present suggested responses to the level of over: project risk exposure or key individual project risks, based on the results of the quantitative risk analysis. the: recommendations will form inputs to the plan risk responses process. | project document that can be consider a output for this process include but be not limit to the risk reportdescribed in section 11.2.3.2. the risk report will be update to reflect the result of the quantitative risk analysis . thiswill typically include : m chance of project success , indicate by the probability that the project will achieve it key objective ( e.g. , required end date or interim milestone , require cost target , etc . ) give the identified individual project risksand other source of uncertainty ; and detail probabilistic analysis of the project . key output from the quantitative risk analysis be presentsuch a s-curves , tornado diagram , and criticality analysis , together with a narrative interpretation of the resupossible detailed result of a quantitative risk analysis may include : m= amount of contingency reserve need to provide a specified level of confidence ; = identification of individual project risk or other source of uncertainty that have the great effect oproject critical path ; andm= major driver of overall project risk , with the great influence on uncertainty in project outcome . trend in quantitative risk analysis result . a the analysis be repeat at different time during the projeccycle , trend may become apparent that inform the planning of risk response . recommend risk response . the risk report may present suggested response to the level of over : project risk exposure or key individual project risk , base on the result of the quantitative risk analysis . the : recommendation will form input to the plan risk responses process .
69 | 11.5 plan risk responses | plan risk responses is the process of developing options, selecting strategies, and agreeing on actions to address overall project risk exposure, as well as to treat individual project risks. the key benefit of this process is that it identifies appropriate ways to address overall project risk and individual project risks. this process also allocates resources and inserts activities into project documents and the project management plan as needed. this process is performed throughout the project. the inputs, tools and techniques, and outputs of the process are depicted in figure 11-16. figure 11-17 depicts the data flow diagram for the process. figure 11-16. plan risk responses: inputs, tools & techniques, and outputs Figure 11-17. Plan Risk Responses: Data Flow Diagram Effective and appropriate risk responses can minimize individual threats, maximize individual opportunities, and reduce overall project risk exposure. Unsuitable risk responses can have the converse effect. Once risks have been identified, analyzed, and prioritized, plans should be developed by the nominated risk owner for addressing every individual project risk the project team considers to be sufficiently important, either because of the threat it poses to the project objectives or the opportunity it offers. The project manager should also consider how to respond appropriately to the current level of overall project risk. Risk responses should be appropriate for the significance of the risk, cost-effective in meeting the challenge, realistic within the project context, agreed upon by all parties involved, and owned by a responsible person. Selecting the optimal risk response from several options is often required. The strategy or mix of strategies most likely to be effective should be selected for each risk. Structured decision-making techniques may be used to choose the most appropriate response. For large or complex projects, it may be appropriate to use a mathematical optimization model or real options analysis as a basis for a more robust economic analysis of alternative risk response strategies. Specific actions are developed to implement the agreed-upon risk response strategy, including primary and ba strategies, as necessary. A contingency plan (or fallback plan) can be developed for implementation if the sele strategy turns out not to be fully effective or if an accepted risk occurs. Secondary risks should also be ident Secondary risks are risks that arise as a direct result of implementing a risk response. A contingency reserve is « allocated for time or cost. If developed, it may include identification of the conditions that trigger its use. | plan risk response be the process of develop option , select strategy , and agree on action to addressoverall project risk exposure , as well a to treat individual project risk . the key benefit of this process be that it identifiesappropriate way to address overall project risk and individual project risk . this process also allocate resourcesand insert activity into project document and the project management plan a need . this process be performedthroughout the project . the input , tool and technique , and output of the process be depict in figure 11-16.figure 11-17 depict the data flow diagram for the process.figure 11-16. plan risk response : input , tool & technique , and outputsfigure 11-17 . plan risk response : data flow diagrameffective and appropriate risk response can minimize individual threat , maximize individual opportunity , andreduce overall project risk exposure . unsuitable risk response can have the converse effect . once risk have beenidentified , analyze , and prioritize , plan should be develop by the nominated risk owner for address everyindividual project risk the project team considers to be sufficiently important , either because of the threat it pose to theproject objective or the opportunity it offer . the project manager should also consider how to respond appropriately tothe current level of overall project risk.risk response should be appropriate for the significance of the risk , cost-effective in meet the challenge , realisticwithin the project context , agree upon by all party involve , and own by a responsible person . select theoptimal risk response from several option be often require . the strategy or mix of strategy most likely to be effectiveshould be select for each risk . structure decision-making technique may be use to choose the most appropriateresponse . for large or complex project , it may be appropriate to use a mathematical optimization model or real optionsanalysis a a basis for a more robust economic analysis of alternative risk response strategies.specific action be develop to implement the agreed-upon risk response strategy , include primary and bastrategies , a necessary . a contingency plan ( or fallback plan ) can be develop for implementation if the selestrategy turn out not to be fully effective or if an accept risk occur . secondary risk should also be identsecondary risk be risk that arise a a direct result of implement a risk response . a contingency reserve be allocate for time or cost . if develop , it may include identification of the condition that trigger it use .
70 | 11.5.1 plan risk responses: inputs
71 | 11.5.1.1 project management plan | described in section 4.2.3.1. project management plan components include but are not limited to: @ resource management plan. described in section 9.1.3.1. the resource management plan is used to help determine how resources allocated to agreed-upon risk responses will be coordinated with other project resources. @ risk management plan. described in section 11.1.3.1. risk management roles and responsibilities and r thresholds are used in this process. @ cost baseline. described in section 7.3.3.1. the cost baseline has information on the contingency fund that is allocated to respond to risks. | describe in section 4.2.3.1. project management plan component include but be not limit to : resource management plan . describe in section 9.1.3.1. the resource management plan be use to helpdetermine how resource allocate to agreed-upon risk response will be coordinate with other project resource . risk management plan . describe in section 11.1.3.1. risk management role and responsibility and rthresholds be use in this process . cost baseline . describe in section 7.3.3.1. the cost baseline have information on the contingency fund that isallocated to respond to risk .
72 | 11.5.1.2 project documents | @ lessons learned register. described in section 4.4.3.1. lessons learned about effective risk responses used in earlier phases of the project are reviewed to determine if similar responses might be useful during the remainder of the project. @ risk register. described in section 11.2.3.1. the risk register contains details of individual project risks that have been identified and prioritized, and for which risk responses are required. the priority level for each risk can help to guide the selection of appropriate risk responses. for example, high-priority threats or opportunities may require priority action and highly proactive response strategies. threats and opportunities in the low-priority zone may not require proactive management action beyond being placed in the risk register as part of the watch list or adding a contingency reserve. the risk register identifies the nominated risk owner for each risk. it may also contain preliminary risk responses identified earlier in the project risk management process. the risk register may provide other data on identified risks that can assist in planning risk responses, including root causes, risk triggers and warning signs, risks requiring responses in the near term, and risks where a need for additional analysis has been identified. @ risk report. described in section 11.2.3.2. the risk report presents the current level of overall risk exposure of the project that will inform selection of the risk response strategy. the risk report may also list individual project risks in priority order and provide additional analysis of the distribution of individual project risks that may inform risk response selection. | lesson learn register . describe in section 4.4.3.1. lesson learn about effective risk response use inearlier phase of the project be review to determine if similar response might be useful during the remainderof the project . risk register . describe in section 11.2.3.1. the risk register contain detail of individual project risk thathave be identify and prioritize , and for which risk response be require . the priority level for each riskcan help to guide the selection of appropriate risk response . for example , high-priority threat or opportunitiesmay require priority action and highly proactive response strategy . threat and opportunity in the low-priorityzone may not require proactive management action beyond be place in the risk register a part of the watchlist or add a contingency reserve.the risk register identify the nominated risk owner for each risk . it may also contain preliminary risk responsesidentified earlier in the project risk management process . the risk register may provide other data on identifiedrisks that can assist in plan risk response , include root cause , risk trigger and warn sign , risksrequiring response in the near term , and risk where a need for additional analysis have be identify . risk report . describe in section 11.2.3.2. the risk report present the current level of overall risk exposure ofthe project that will inform selection of the risk response strategy . the risk report may also list individual projectrisks in priority order and provide additional analysis of the distribution of individual project risk that may informrisk response selection .
73 | 11.5.1.3 enterprise environmental factors | the enterprise environmental factors that can influence the plan risk responses process include but are not limited to the risk appetite and thresholds of key stakeholders. | the enterprise environmental factor that can influence the plan risk responses process include but be not limitedto the risk appetite and threshold of key stakeholder .
74 | 11.5.1.4 organizational process assets | the organizational process assets that can influence the plan risk responses process include but are @ templates for the risk management plan, risk register, and risk report; - litt anal aatnhanaas oe | the organizational process asset that can influence the plan risk responses process include but be template for the risk management plan , risk register , and risk report ; - litt anal aatnhanaas oe
75 | 11.5.2 plan risk responses: tools and techniques
76 | 11.5.2.1 expert judgment | described in section 4.1.2.1. expertise should be considered from individuals or groups with specialized knowlec in the following topics: | describe in section 4.1.2.1. expertise should be consider from individual or group with specialized knowlecin the following topic :
77 | 11.5.2.2 data gathering | data-gathering techniques that can be used for this process include but are not limited to interviews (see section 5.2.2.2). development of responses to individual project risks and overall project risk may be undertaken during structured or semi-structured interviews (see section 5.2.2.2) with risk owners. other stakeholders may also be interviewed if necessary. the interviewer should promote an environment of trust and confidentiality in the interview setting to encourage honest and unbiased decisions. | data-gathering technique that can be use for this process include but be not limit to interview ( seesection 5.2.2.2 ) . development of response to individual project risk and overall project risk may be undertakenduring structured or semi-structured interview ( see section 5.2.2.2 ) with risk owner . other stakeholder mayalso be interview if necessary . the interviewer should promote an environment of trust and confidentiality in theinterview set to encourage honest and unbiased decision .
78 | 11.5.2.3 interpersonal and team skills | interpersonal and team skills that can be used for this process includes but are not limited to facilitation (see section 4.1.2.3). the use of facilitation improves the effectiveness of developing responses to individual project risks and overall project risk. a skilled facilitator can help risk owners understand the risk, identify and compare alternative possible risk response strategies, choose an appropriate response strategy, and identify and overcome eniirroac nf hing | interpersonal and team skill that can be use for this process include but be not limit to facilitation ( seesection 4.1.2.3 ) . the use of facilitation improve the effectiveness of develop response to individual projectrisks and overall project risk . a skilled facilitator can help risk owner understand the risk , identify and comparealternative possible risk response strategy , choose an appropriate response strategy , and identify and overcomeeniirroac nf hing
79 | 11.5.2.4 strategies for threats | five alternative strategies may be considered for dealing with threats, as follows: @ escalate. escalation is appropriate when the project team or the project sponsor agrees that a threat is outside the scope of the project or that the proposed response would exceed the project manager’s authority. escalated risks are managed at the program level, portfolio level, or other relevant part of the organization, and not on the project level. the project manager determines who should be notified about the threat and communicates the details to that person or part of the organization. it is important that ownership of escalated threats is accepted by the relevant party in the organization. threats are usually escalated to the level that matches the objectives that would be affected if the threat occurred. escalated threats are not monitored further by the project team after escalation, although they may be recorded in the risk register for information. @ Avoid. Risk avoidance is when the project team acts to eliminate the threat or protect the project from its impact. It may be appropriate for high-priority threats with a high probability of occurrence and a large negative impact. Avoidance may involve changing some aspect of the project management plan or changing the objective that is in jeopardy in order to eliminate the threat entirely, reducing its probability of occurrence to zero. The risk owner may also take action to isolate the project objectives from the risk’s impact if it were to occur. Examples of avoidance actions may include removing the cause of a threat, extending the schedule, changing the project strategy, or reducing scope. Some risks can be avoided by clarifying requirements, obtaining information, improving communication, or acquiring expertise. @ Transfer. Transfer involves shifting ownership of a threat to a third party to manage the risk and to bear the impact if the threat occurs. Risk transfer often involves payment of a risk premium to the party taking on the threat. Transfer can be achieved by a range of actions, which include but are not limited to the use of insurance, performance bonds, warranties, guarantees, etc. Agreements may be used to transfer ownership and liability for specified risks to another party. @ Mitigate. In risk mitigation, action is taken to reduce the probability of occurrence and/or impact of a threat. Early mitigation action is often more effective than trying to repair the damage after the threat has occurred. Adopting less complex processes, conducting more tests, or choosing a more stable seller are examples of mitigation actions. Mitigation may involve prototype development (see Section 5.2.2.8) to reduce the risk of scaling up from a bench-scale model of a process or product. Where it is not possible to reduce probability, a mitigation response might reduce the impact by targeting factors that drive the severity. For example, designing redundancy into a system may reduce the impact from a failure of the original component. @ Accept. Risk acceptance acknowledges the existence of a threat, but no proactive action is taken. This strategy may be appropriate for low-priority threats, and it may also be adopted where it is not possible or cost-effective to address a threat in any other way. Acceptance can be either active or passive. The most common active acceptance strategy is to establish a contingency reserve, including amounts of time, money, or resources to handle the threat if it occurs. Passive acceptance involves no proactive action apart from periodic review of the threat to ensure that it does not change significantly. | five alternative strategy may be consider for deal with threat , a follow : escalate . escalation be appropriate when the project team or the project sponsor agree that a threat be outsidethe scope of the project or that the propose response would exceed the project manager ’ s authority . escalatedrisks be manage at the program level , portfolio level , or other relevant part of the organization , and not on theproject level . the project manager determines who should be notify about the threat and communicate thedetails to that person or part of the organization . it be important that ownership of escalated threat be acceptedby the relevant party in the organization . threat be usually escalate to the level that match the objectivesthat would be affect if the threat occur . escalate threat be not monitor far by the project team afterescalation , although they may be record in the risk register for information . avoid . risk avoidance be when the project team act to eliminate the threat or protect the project from itsimpact . it may be appropriate for high-priority threat with a high probability of occurrence and a large negativeimpact . avoidance may involve change some aspect of the project management plan or change the objectivethat be in jeopardy in order to eliminate the threat entirely , reduce it probability of occurrence to zero . therisk owner may also take action to isolate the project objectives from the risk ’ s impact if it be to occur.examples of avoidance action may include remove the cause of a threat , extend the schedule , change theproject strategy , or reduce scope . some risk can be avoid by clarify requirement , obtain information , improve communication , or acquire expertise . transfer . transfer involve shift ownership of a threat to a third party to manage the risk and to bear theimpact if the threat occur . risk transfer often involve payment of a risk premium to the party take on thethreat . transfer can be achieve by a range of action , which include but be not limit to the use of insurance , performance bond , warranty , guarantee , etc . agreement may be use to transfer ownership and liability forspecified risk to another party . mitigate . in risk mitigation , action be take to reduce the probability of occurrence and/or impact of a threat . earlymitigation action be often more effective than try to repair the damage after the threat have occur . adoptingless complex process , conduct more test , or choose a more stable seller be example of mitigationactions . mitigation may involve prototype development ( see section 5.2.2.8 ) to reduce the risk of scale up froma bench-scale model of a process or product . where it be not possible to reduce probability , a mitigation responsemight reduce the impact by target factor that drive the severity . for example , design redundancy into asystem may reduce the impact from a failure of the original component . accept . risk acceptance acknowledge the existence of a threat , but no proactive action be take . this strategymay be appropriate for low-priority threat , and it may also be adopt where it be not possible or cost-effectiveto address a threat in any other way . acceptance can be either active or passive . the most common activeacceptance strategy be to establish a contingency reserve , include amount of time , money , or resource tohandle the threat if it occur . passive acceptance involve no proactive action apart from periodic review of thethreat to ensure that it do not change significantly .
80 | 11.5.2.5 strategies for opportunities | five alternative strategies may be considered for dealing with opportunities, as follows: five alternative strategies may be considered for dealing with opportunities, as follows: @ escalate. this risk response strategy is appropriate when the project team or the project sponsor agrees that an opportunity is outside the scope of the project or that the proposed response would exceed the project manager’s authority. escalated opportunities are managed at the program level, portfolio level, or other relevant part of the organization, and not on the project level. the project manager determines who should be notified about the opportunity and communicates the details to that person or part of the organization. it is important that ownership of escalated opportunities is accepted by the relevant party in the organization. opportunities are usually escalated to the level that matches the objectives that would be affected if the opportunity occurred. escalated opportunities are not monitored further by the project team after escalation, although they may be recorded in the risk register for information. @ exploit. the exploit strategy may be selected for high-priority opportunities where the organization wants to ensure that the opportunity is realized. this strategy seeks to capture the benefit associated with a particular opportunity by ensuring that it definitely happens, increasing the probability of occurrence to 100%. examples of exploiting responses may include assigning an organization’s most talented resources to the project to reduce the time to completion, or using new technologies or technology upgrades to reduce cost and duration. @ share. sharing involves transferring ownership of an opportunity to a third party so that it shares some of the benefit if the opportunity occurs. it is important to select the new owner of a shared opportunity carefully so they are best able to capture the opportunity for the benefit of the project. risk sharing often involves payment of a risk premium to the party taking on the opportunity. examples of sharing actions include forming risk-sharing partnerships, teams, special-purpose companies, or joint ventures. @ enhance. the enhance strategy is used to increase the probability and/or impact of an opportunity. early enhancement action is often more effective than trying to improve the benefit after the opportunity has occurred. the probability of occurrence of an opportunity may be increased by focusing attention on its causes. where it is not possible to increase probability, an enhancement response might increase the impact by targeting factors that drive the size of the potential benefit. examples of enhancing opportunities include adding more resources to an activity to finish early. @ accept. accepting an opportunity acknowledges its existence but no proactive action is taken. this strategy may be appropriate for low-priority opportunities, and it may also be adopted where it is not possible or cost-effective to address an opportunity in any other way. acceptance can be either active or passive. the most common active acceptance strategy is to establish a contingency reserve, including amounts of time, money, or resources to take advantage of the opportunity if it occurs. passive acceptance involves no proactive action apart from periodic review of the opportunity to ensure that it does not change significantly. | five alternative strategy may be consider for deal with opportunity , a follow : five alternative strategy may be consider for deal with opportunity , a follow : escalate . this risk response strategy be appropriate when the project team or the project sponsor agree thatan opportunity be outside the scope of the project or that the propose response would exceed the projectmanager ’ s authority . escalate opportunity be manage at the program level , portfolio level , or other relevantpart of the organization , and not on the project level . the project manager determines who should be notifiedabout the opportunity and communicate the detail to that person or part of the organization . it be importantthat ownership of escalated opportunity be accept by the relevant party in the organization . opportunitiesare usually escalate to the level that match the objective that would be affect if the opportunity occurred.escalated opportunity be not monitor far by the project team after escalation , although they may berecorded in the risk register for information . exploit . the exploit strategy may be select for high-priority opportunity where the organization want toensure that the opportunity be realize . this strategy seek to capture the benefit associate with a particularopportunity by ensure that it definitely happen , increase the probability of occurrence to 100 % . example ofexploiting response may include assign an organization ’ s most talented resource to the project to reducethe time to completion , or use new technology or technology upgrade to reduce cost and duration . share . share involves transfer ownership of an opportunity to a third party so that it share some of thebenefit if the opportunity occur . it be important to select the new owner of a share opportunity carefully so theyare best able to capture the opportunity for the benefit of the project . risk share often involve payment of arisk premium to the party take on the opportunity . example of share action include form risk-sharingpartnerships , team , special-purpose company , or joint venture . enhance . the enhance strategy be use to increase the probability and/or impact of an opportunity . earlyenhancement action be often more effective than try to improve the benefit after the opportunity have occurred.the probability of occurrence of an opportunity may be increase by focus attention on it cause . where itis not possible to increase probability , an enhancement response might increase the impact by target factorsthat drive the size of the potential benefit . example of enhance opportunity include add more resourcesto an activity to finish early . accept . accept an opportunity acknowledge it existence but no proactive action be take . this strategy maybe appropriate for low-priority opportunity , and it may also be adopt where it be not possible or cost-effectiveto address an opportunity in any other way . acceptance can be either active or passive . the most common activeacceptance strategy be to establish a contingency reserve , include amount of time , money , or resource to takeadvantage of the opportunity if it occur . passive acceptance involve no proactive action apart from periodicreview of the opportunity to ensure that it do not change significantly .
81 | 11.5.2.6 contingent response strategies | some responses are designed for use only if certain events occur. for some risks, it is appropriate for the project team to make a response plan that will only be executed under certain predefined conditions, if it is believed that there will be sufficient warning to implement the plan. events that trigger the contingency response, such as missing intermediate milestones or gaining higher priority with a seller, should be defined and tracked. risk responses identified using this technique are often called contingency plans or fallback plans and include identified triggering events that set the plans in effect. | some response be design for use only if certain event occur . for some risk , it be appropriate for the projectteam to make a response plan that will only be execute under certain predefined condition , if it be believe thatthere will be sufficient warning to implement the plan . event that trigger the contingency response , such a missingintermediate milestone or gain high priority with a seller , should be define and track . risk responsesidentified use this technique be often call contingency plan or fallback plan and include identify triggeringevents that set the plan in effect .
82 | 11.5.2.7 strategies for overall project risk | risk responses should be planned and implemented not only for individual project risks but also to address overall project risk. the same risk response strategies that are used to deal with individual project risks can also be applied to overall project risk: @ avoid. where the level of overall project risk is significantly negative and outside the agreed-upon risk thresholds for the project, an avoid strategy may be adopted. this involves taking focused action to reduce the negative effect of uncertainty on the project as a whole and bring the project back within the thresholds. an example of avoidance at the overall project level would include removal of high-risk elements of scope from the project. where it is not possible to bring the project back within the thresholds, the project may be canceled. this represents the most extreme degree of risk avoidance and it should be used only if the overall level of threat is, and will remain, unacceptable. @ exploit. where the level of overall project risk is significantly positive and outside the agreed-upon risk thresholds for the project, an exploit strategy may be adopted. this involves taking focused action to capture the positive effect of uncertainty on the project as a whole. an example of exploiting at the overall project level would include addition of high-benefit elements of scope to the project to add value or benefits to stakeholders. alternatively the risk thresholds for the project may be modified with the agreement of key stakeholders in order to embrace the opportunity. @ transfer/share. if the level of overall project risk is high but the organization is unable to address it effectively, a third party may be involved to manage the risk on behalf of the organization. where overall project risk is negative, a transfer strategy is required, which may involve payment of a risk premium. in the case of high positive overall project risk, ownership may be shared in order to reap the associated benefits. examples of both transfer and share strategies for overall project risk include but are not limited to setting up a collaborative business structure in which the buyer and the seller share the overall project risk, launching a joint venture or special-purpose company, or subcontracting key elements of the project. @ Mitigate/enhance. These strategies involve changing the level of overall project risk to optimize the chances of achieving the project’s objectives. The mitigation strategy is used where overall project risk is negative, anc enhancement applies when it is positive. Examples of mitigation or enhancement strategies include replanninc the project, changing the scope and boundaries of the project, modifying project priority, changing resource allocations, adjusting delivery times, etc. @ Accept. Where no proactive risk response strategy is possible to address overall project risk, the organizatio may choose to continue with the project as currently defined, even if overall project risk is outside the agreec upon thresholds. Acceptance can be either active or passive. The most common active acceptance strategy i to establish an overall contingency reserve for the project, including amounts of time, money, or resources to b used if the project exceeds its thresholds. Passive acceptance involves no proactive action apart from periodi review of the level of overall project risk to ensure that it does not change significantly. | risk response should be plan and implement not only for individual project risk but also to address overallproject risk . the same risk response strategy that be use to deal with individual project risk can also be apply tooverall project risk : avoid . where the level of overall project risk be significantly negative and outside the agreed-upon riskthresholds for the project , an avoid strategy may be adopt . this involve take focused action to reducethe negative effect of uncertainty on the project a a whole and bring the project back within the thresholds.an example of avoidance at the overall project level would include removal of high-risk element of scopefrom the project . where it be not possible to bring the project back within the threshold , the project may becanceled . this represent the most extreme degree of risk avoidance and it should be use only if the overalllevel of threat be , and will remain , unacceptable . exploit . where the level of overall project risk be significantly positive and outside the agreed-upon risk thresholdsfor the project , an exploit strategy may be adopt . this involve take focused action to capture the positiveeffect of uncertainty on the project a a whole . an example of exploit at the overall project level would includeaddition of high-benefit element of scope to the project to add value or benefit to stakeholder . alternativelythe risk threshold for the project may be modify with the agreement of key stakeholder in order to embracethe opportunity . transfer/share . if the level of overall project risk be high but the organization be unable to address it effectively , a third party may be involve to manage the risk on behalf of the organization . where overall project risk isnegative , a transfer strategy be require , which may involve payment of a risk premium . in the case of highpositive overall project risk , ownership may be share in order to reap the associated benefit . example ofboth transfer and share strategy for overall project risk include but be not limit to set up a collaborativebusiness structure in which the buyer and the seller share the overall project risk , launch a joint venture orspecial-purpose company , or subcontract key element of the project . mitigate/enhance . these strategy involve change the level of overall project risk to optimize the chancesof achieve the project ’ s objective . the mitigation strategy be use where overall project risk be negative , ancenhancement applies when it be positive . example of mitigation or enhancement strategy include replannincthe project , change the scope and boundary of the project , modify project priority , change resourceallocations , adjust delivery time , etc . accept . where no proactive risk response strategy be possible to address overall project risk , the organizatiomay choose to continue with the project a currently define , even if overall project risk be outside the agreecupon threshold . acceptance can be either active or passive . the most common active acceptance strategy ito establish an overall contingency reserve for the project , include amount of time , money , or resource to bus if the project exceed it threshold . passive acceptance involve no proactive action apart from periodireview of the level of overall project risk to ensure that it do not change significantly .
83 | 11.5.2.8 data analysis | @ cost-benefit analysis. if the impact of an individual project risk can be quantified in monetary terms, then the cost-effectiveness of alternative risk response strategies can be determined using cost-benefit analysis (see section 8.1.2.3). the ratio of (change in impact level) divided by (implementation cost) gives the cost effectiveness of the response strategy, with a higher ratio indicating a more effective response. | cost-benefit analysis . if the impact of an individual project risk can be quantify in monetary term , then thecost-effectiveness of alternative risk response strategy can be determine use cost-benefit analysis ( seesection 8.1.2.3 ) . the ratio of ( change in impact level ) divide by ( implementation cost ) give the cost effectivenessof the response strategy , with a high ratio indicate a more effective response .
84 | 11.5.2.9 decision making | decision-making techniques that can be used to select a risk response strategy include but are not limited to multicriteria decision analysis (described in section 8.1.2.4). one or more risk response strategies may be under consideration. decision-making techniques can help prioritize risk response strategies. multicriteria decision analysis uses a decision matrix to provide a systematic approach for establishing key decision criteria, evaluating and ranking alternatives, and selecting a preferred option. criteria for risk response selection may include but are not limited to cost of response, likely effectiveness of response in changing probability and/or impact, resource availability, timing constraints (urgency, proximity, and dormancy), level of impact if the risk occurs, effect of response on related risks, introduction of secondary risks, etc. different strategies may be selected later in the project if the original choice proves to be ineffective. | decision-making technique that can be use to select a risk response strategy include but be not limited tomulticriteria decision analysis ( describe in section 8.1.2.4 ) . one or more risk response strategy may be underconsideration . decision-making technique can help prioritize risk response strategy . multicriteria decision analysisuses a decision matrix to provide a systematic approach for establish key decision criterion , evaluate and rankingalternatives , and select a preferred option . criterion for risk response selection may include but be not limited tocost of response , likely effectiveness of response in change probability and/or impact , resource availability , timingconstraints ( urgency , proximity , and dormancy ) , level of impact if the risk occur , effect of response on related risk , introduction of secondary risk , etc . different strategy may be select later in the project if the original choice provesto be ineffective .
85 | 11.5.3 plan risk responses: outputs
86 | 11.5.3.1 change requests | described in section 4.3.3.4. planned risk responses may result in a change request to the cost and schedul baselines or other components of the project management plan. change requests are processed for review ani disposition through the perform integrated change control process (section 4.6). | describe in section 4.3.3.4. plan risk response may result in a change request to the cost and schedulbaselines or other component of the project management plan . change request be process for review anidisposition through the perform integrated change control process ( section 4.6 ) .
87 | 11.5.3.2 project management plan updates | fe ee ror re rs nn, lse gry ere re any change to the project management plan goes through the organization’s change control process via a change request. components that may require a change request for the project management plan include but are not limited to: @ cost management plan. described in section 7.1.3.1. changes to the cost management plan, such as changes to cost accounting, tracking, and reports, as well as updates to the budget strategy and how contingency reserves are consumed, are incorporated. @ quality management plan. described in section 8.1.3.1. changes to the quality management plan, such as changes to approaches for meeting requirements, quality management approaches, or quality control processes, are incorporated. @ scope baseline. described in section 5.4.3.1. changes in the scope baseline are incorporated in respon: approved changes in scope that may arise from agreed-upon risk responses. @ schedule baseline. described in section 6.5.3.1. changes in the schedule baseline are incorporated in response to approved changes in schedule estimates that may arise from agreed-upon risk responses. @ cost baseline. described in section 7.3.3.1. changes in the cost baseline are incorporated in re approved changes in cost estimates that may arise from agreed-upon risk responses. | fe ee ror re r nn , lse gry ere reany change to the project management plan go through the organization ’ s change control process via a changerequest . component that may require a change request for the project management plan include but be not limit to : cost management plan . describe in section 7.1.3.1. change to the cost management plan , such a changesto cost accounting , track , and report , as well a update to the budget strategy and how contingency reservesare consume , be incorporate . quality management plan . describe in section 8.1.3.1. change to the quality management plan , such aschanges to approach for meeting requirement , quality management approach , or quality control process , be incorporate . scope baseline . describe in section 5.4.3.1. change in the scope baseline be incorporate in respon : approve change in scope that may arise from agreed-upon risk response . schedule baseline . describe in section 6.5.3.1. change in the schedule baseline be incorporate in responseto approve change in schedule estimate that may arise from agreed-upon risk response . cost baseline . describe in section 7.3.3.1. change in the cost baseline be incorporate in reapproved change in cost estimate that may arise from agreed-upon risk response .
88 | 11.5.3.3 project documents updates | @ assumption log. described in section 4.1.3.2. during the plan risk responses process, new assumptions may be made, new constraints may be identified, and existing assumptions or constraints may be revisited and changed. the assumption log should be updated with this new information. @ cost forecasts. described in section 7.4.3.2. cost forecasts may change as a result of planned risk responses. - lessons learned register. described in section 4.4.3.1. the lessons learned register is updated with information about risk responses that may be useful for future phases of the project or future projects. @ project team assignments. described in section 9.3.3.2. once the responses are confirmed, the necessar resources should be allocated to each action associated with a risk response plan. these resources include suitabl qualified and experienced personnel to execute the agreed-upon action (usually within the project team) a specifi budget and time allowance for the action, and any required technical resources to complete the action. @ risk register. described in section 11.2.3.1. the risk register is updated when appropriate risk ¦ chosen and agreed upon. updates to the risk register may include but are not limited to: ww mick poyiolce, voouiivou tt oouuutl t1.2.0.1. tio thor poyiouc! lo upuglou which! gvviumiialg tok tgop! chosen and agreed upon. updates to the risk register may include but are not limited to: agreed-upon response strategies; specific actions to implement the chosen response strategy; trigger conditions, symptoms, and warning signs of a risk occurrence; budget and schedule activities required to implement the chosen responses; contingency plans and risk triggers that call for their execution; fallback plans for use when a risk that has occurred and the primary response proves to be inadec residual risks that are expected to remain after planned responses have been taken, as well as t have been deliberately accepted; and m secondary risks that arise as a direct outcome of implementing a risk response. @ risk report. described in section 11.2.3.2. the risk report may be updated to present agreed-upon r @ risk report. described in section 11.2.3.2. the risk report may be updated to present agreed-upon responses to the current overall project risk exposure and high-priority risks, together with the expected changes that may be expected as a result of implementing these responses. | assumption log . describe in section 4.1.3.2. during the plan risk response process , new assumptionsmay be make , new constraint may be identify , and exist assumption or constraint may be revisit andchanged . the assumption log should be update with this new information . cost forecast . describe in section 7.4.3.2. cost forecast may change a a result of plan risk responses.- lesson learn register . describe in section 4.4.3.1. the lesson learn register be update with informationabout risk response that may be useful for future phase of the project or future project . project team assignment . describe in section 9.3.3.2. once the response be confirm , the necessarresources should be allocate to each action associate with a risk response plan . these resource include suitablqualified and experienced personnel to execute the agreed-upon action ( usually within the project team ) a specifibudget and time allowance for the action , and any required technical resource to complete the action . risk register . describe in section 11.2.3.1. the risk register be update when appropriate risk ¦chosen and agree upon . update to the risk register may include but be not limit to : ww mick poyiolce , voouiivou tt oouuutl t1.2.0.1 . tio thor poyiouc ! lo upuglou which ! gvviumiialg tok tgop ! chosen and agree upon . update to the risk register may include but be not limit to : agreed-upon response strategy ; specific action to implement the chosen response strategy ; trigger condition , symptom , and warn sign of a risk occurrence ; budget and schedule activity require to implement the chosen responses ; contingency plan and risk trigger that call for their execution ; fallback plan for use when a risk that have occur and the primary response prove to be inadecresidual risk that be expect to remain after planned response have be take , as well a thave be deliberately accept ; andm secondary risk that arise a a direct outcome of implement a risk response . risk report . describe in section 11.2.3.2. the risk report may be update to present agreed-upon r risk report . describe in section 11.2.3.2. the risk report may be update to present agreed-upon responsesto the current overall project risk exposure and high-priority risk , together with the expect change that maybe expect a a result of implement these response .
89 | 11.6 implement risk responses | implement risk responses is the process of implementing agreed-upon risk response plans. the key benefit this process is that it ensures that agreed-upon risk responses are executed as planned in order to address over project risk exposure, minimize individual project threats, and maximize individual project opportunities. this process performed throughout the project. the inputs, tools and techniques, and outputs of the process are depicted in figu 11-18. figure 11-19 depicts the data flow diagram for the process. figure 11-18. implement risk responses: inputs, tools & techniques, and outputs figure 11-19. implement risk responses: data flow diagram Proper attention to the Implement Risk Responses process will ensure that agreed-upon risk responses are actually executed. A common problem with Project Risk Management is that project teams spend effort in identifying and analyzing risks and developing risk responses, then risk responses are agreed upon and documented in the risk register and risk report, but no action is taken to manage the risk. | implement risk response be the process of implement agreed-upon risk response plan . the key benefitthis process be that it ensure that agreed-upon risk response be execute a plan in order to address overproject risk exposure , minimize individual project threat , and maximize individual project opportunity . this processperformed throughout the project . the input , tool and technique , and output of the process be depict in figu11-18 . figure 11-19 depict the data flow diagram for the process.figure 11-18. implement risk response : input , tool & technique , and outputsfigure 11-19. implement risk response : data flow diagramproper attention to the implement risk response process will ensure that agreed-upon risk response be actuallyexecuted . a common problem with project risk management be that project team spend effort in identify andanalyzing risk and develop risk response , then risk response be agree upon and document in the risk registerand risk report , but no action be take to manage the risk .
90 | 11.6.1 implement risk responses: inputs
91 | 11.6.1.1 project management plan | described in section 4.2.3.1. project management plan components include but are not limited to the risk management plan. described in section 11.1.3.1, the risk management plan lists the roles and responsibilities of project team members and other stakeholders for risk management. this information is used when allocating owners for agreed-upon risk responses. the risk management plan also defines the level of detail for the risk management methodology for the project. it also specifies risk thresholds for the project based on the risk appetite of key stakeholders, which define the acceptable target that the implementation of risk responses is required to achieve. | describe in section 4.2.3.1. project management plan component include but be not limit to the riskmanagement plan . describe in section 11.1.3.1 , the risk management plan list the role and responsibility ofproject team member and other stakeholder for risk management . this information be use when allocate ownersfor agreed-upon risk response . the risk management plan also define the level of detail for the risk managementmethodology for the project . it also specify risk threshold for the project base on the risk appetite of key stakeholder , which define the acceptable target that the implementation of risk response be require to achieve .
92 | 11.6.1.2 project documents | project documents that can be considered as inputs for this process include but are not limited to: @ lessons learned register. described in section 4.4.3.1. lessons learned earlier in the project with regard to implementing risk responses can be applied to later phases in the project to improve the effectiveness of this process. @ risk report. described in section 11.2.3.2. the risk report includes an assessment of the current overall project risk exposure, as well as the agreed-upon risk response strategy. it also describes the major individual project risks with their planned responses. | project document that can be consider a input for this process include but be not limit to : lesson learn register . describe in section 4.4.3.1. lesson learn earlier in the project with regardto implement risk response can be apply to later phase in the project to improve the effectivenessof this process . risk report . describe in section 11.2.3.2. the risk report include an assessment of the current overall projectrisk exposure , as well a the agreed-upon risk response strategy . it also describe the major individual projectrisks with their planned response .
93 | 11.6.1.3 organizational process assets | the organizational process assets that can influence the implement risk responses process include but are not limited to the lessons learned repository from similar completed projects that indicate the effectiveness of particular risk responses. | the organizational process asset that can influence the implement risk response process include but be notlimited to the lesson learn repository from similar complete project that indicate the effectiveness of particularrisk response .
94 | 11.6.2 implement risk responses: tools and techniques
95 | 11.6.2.1 expert judgment | described in section 4.1.2.1. expertise should be considered from individuals or groups with specialized knowledge to validate or modify risk responses if necessary, and decide how to implement them in the most efficient and effective manner. | describe in section 4.1.2.1. expertise should be consider from individual or group with specializedknowledge to validate or modify risk response if necessary , and decide how to implement them in the mostefficient and effective manner .
96 | 11.6.2.2 interpersonal and team skills | interpersonal and team skills that can be used for this process include but are not limited to influencing. some risk 2sponse actions may be owned by people outside the immediate project team or who have other competing demands. he project manager or person responsible for facilitating the risk process may need to exercise influencing (see ection 9.5.2.1) to encourage nominated risk owners to take necessary action where required. | interpersonal and team skill that can be use for this process include but be not limit to influence . some risk2sponse action may be own by people outside the immediate project team or who have other compete demands.he project manager or person responsible for facilitate the risk process may need to exercise influencing ( seeection 9.5.2.1 ) to encourage nominate risk owner to take necessary action where require .
97 | 11.6.2.3 project management information system (pmis) | described in section 4.3.2.2. project management information systems can include schedule, resource, and co ftware to ensure that agreed-upon risk response plans and their associated activities are integrated into the proje mngside other project activities. | describe in section 4.3.2.2. project management information system can include schedule , resource , and coftware to ensure that agreed-upon risk response plan and their associated activity be integrate into the projemngside other project activity .
98 | 11.6.3 implement risk responses: outputs
99 | 11.6.3.1 change requests | described in section 4.3.3.4. implementation of risk responses may result in a change request to the cost and schedule baselines or other components of the project management plan. change requests are processed for review and disposition through the perform integrated change control process (section 4.6). | describe in section 4.3.3.4. implementation of risk response may result in a change request to the cost andschedule baseline or other component of the project management plan . change request be process for reviewand disposition through the perform integrated change control process ( section 4.6 ) .
100 | 11.6.3.2 project documents updates | project documents that may be updated as a result of carrying out this process include but are not limited to: @ issue log. described in section 4.3.3.3. where issues are identified as part of the implement risk respon: process, they are recorded in the issue log. @ lessons learned register. described in section 4.4.3.1. the lessons learned register is updated with information on challenges encountered when implementing risk responses and how they could have been avoided, as well as approaches that worked well for implementing risk responses. @ project team assignments. described in section 9.3.3.2. once the risk responses are confirmed, the necessary resources should be allocated to each action associated with a risk response plan. these resources include suitably qualified and experienced personnel to execute the agreed-upon action (usually within the project team), a specific budget and time allowance for the action, and any required technical resources to complete the action. @ risk register. described in section 11.2.3.1. the risk register may be updated to reflect any changes to the previously agreed-upon risk responses for individual project risks that are subsequently made as a result of the implement risk responses process. @ risk report. described in section 11.2.3.2. the risk report may be updated to reflect any changes to the previously agreed-upon risk response to overall project risk exposure that are subsequently made as a result of the implement risk responses process. | project document that may be update a a result of carry out this process include but be not limit to : issue log . describe in section 4.3.3.3. where issue be identify a part of the implement risk respon : process , they be record in the issue log . lesson learn register . describe in section 4.4.3.1. the lesson learn register be update with informationon challenge encounter when implement risk response and how they could have be avoid , a wellas approach that work well for implement risk response . project team assignment . describe in section 9.3.3.2. once the risk response be confirm , the necessaryresources should be allocate to each action associate with a risk response plan . these resource includesuitably qualify and experience personnel to execute the agreed-upon action ( usually within the project team ) , a specific budget and time allowance for the action , and any required technical resource to complete the action . risk register . describe in section 11.2.3.1. the risk register may be update to reflect any change to thepreviously agreed-upon risk response for individual project risk that be subsequently make a a result of theimplement risk response process . risk report . describe in section 11.2.3.2. the risk report may be update to reflect any change to thepreviously agreed-upon risk response to overall project risk exposure that be subsequently make a a result ofthe implement risk response process .
101 | 11.7 monitor risks | monitor risks is the process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. the key benefit of this process is that it enables project decisions to be based on current information about overall project risk exposure and individual project risks. this process is performed throughout the project. the inputs, tools and techniques, and outputs of the process are depicted in figure 11-20. figure 11-21 depicts the data flow diagram for the process. figure 11-20. monitor risks: inputs, tools & techniques, and output: Figure 11-21. Monitor Risks: Data Flow Diagram In order to ensure that the project team and key stakeholders are aware of the current level of risk exposure, project work should be continuously monitored for new, changing, and outdated individual project risks and for changes in the level of overall project risk by applying the Monitor Risks process. The Monitor Risks process uses performance information generated during project execution to determine if: Information generated during project execution to determine If: @ Implemented risk responses are effective, @ Level of overall project risk has changed, @ Status of identified individual project risks has changed, @ New individual project risks have arisen, @ Risk management approach is still appropriate, @ Project assumptions are still valid, @ Risk management policies and procedures are being followed, @ Contingency reserves for cost or schedule require modification, anc @ Project strategy is still valid. | monitor risk be the process of monitor the implementation of agreed-upon risk response plan , track identifiedrisks , identify and analyze new risk , and evaluate risk process effectiveness throughout the project . the keybenefit of this process be that it enable project decision to be base on current information about overall project riskexposure and individual project risk . this process be perform throughout the project . the input , tool and technique , and output of the process be depict in figure 11-20. figure 11-21 depict the data flow diagram for the process.figure 11-20. monitor risk : input , tool & technique , and output : figure 11-21 . monitor risk : data flow diagramin order to ensure that the project team and key stakeholder be aware of the current level of risk exposure , projectwork should be continuously monitor for new , changing , and outdated individual project risk and for change inthe level of overall project risk by apply the monitor risk process . the monitor risk process use performanceinformation generate during project execution to determine if : information generate during project execution to determine if : implement risk response be effective , level of overall project risk have change , status of identify individual project risk have change , new individual project risk have arise , risk management approach be still appropriate , project assumption be still valid , risk management policy and procedure be be follow , contingency reserve for cost or schedule require modification , anc project strategy be still valid .
102 | 11.7.1 monitor risks: inputs
103 | 11.7.1.1 project management plan | described in section 4.2.3.1. project management plan components include but are not limited to the risk management plan. described in section 11.3.1.1. the risk management plan provides guidance on how and when risks should be reviewed, which policies and procedures should be followed, the roles and responsibilities in the monitoring process. and reporting formats. | describe in section 4.2.3.1. project management plan component include but be not limit to the riskmanagement plan . describe in section 11.3.1.1. the risk management plan provide guidance on how and whenrisks should be review , which policy and procedure should be follow , the role and responsibility in themonitoring process . and report format .
104 | 11.7.1.2 project documents | project documents that should be considered as inputs for this process include but are not limited to: @ risk register. described in section 11.2.3.1. the risk register has key inputs that include identified individual project risks, risk owners, agreed-upon risk responses, and specific implementation actions. it may also provide other details including control actions for assessing the effectiveness of response plans, symptoms and warning signs of risk, residual and secondary risks, and a watch list of low-priority risks. > risk report. described in section 11.2.3.2. the risk report includes an assessment of the current overall project risk exposure as well as the agreed-upon risk response strategy. it also describes the major individual risks with planned responses and risk owners. | project document that should be consider a input for this process include but be not limit to : risk register . describe in section 11.2.3.1. the risk register have key input that include identified individualproject risk , risk owner , agreed-upon risk response , and specific implementation action . it may also provideother detail include control action for assess the effectiveness of response plan , symptom and warningsigns of risk , residual and secondary risk , and a watch list of low-priority risks. > risk report . describe in section 11.2.3.2. the risk report include an assessment of the current overall projectrisk exposure as well a the agreed-upon risk response strategy . it also describe the major individual risk withplanned response and risk owner .
105 | 11.7.1.3 work performance data | © ea sss ec described in section 4.3.3.2. work performance data contains data on project status such as risk response have been implemented, risks that have occurred, risks that are active and those that have been closed out. | ea ss ecdescribed in section 4.3.3.2. work performance data contains data on project status such a risk responsehave be implement , risk that have occur , risk that be active and those that have be close out .
106 | 11.7.1.4 work performance reports | described in section 4 5.3.1. work performance reports provide information from performance measurements t can be analyzed to provide project work performance information including variance analysis, earned value data, < forecasting data. this information could be relevant when monitoring performance-related risks. | describe in section 4 5.3.1. work performance report provide information from performance measurement tcan be analyze to provide project work performance information include variance analysis , earn value data , < forecast data . this information could be relevant when monitor performance-related risk .
107 | 11.7.2 monitor risks: tools and techniques
108 | 11.7.2.1 data analysis | data analysis techniques that can be used for this process include but are not limited to: @ technical performance analysis. technical performance analysis compares technical accomplishments durin project execution to the schedule of technical achievement. it requires the definition of objective, quantifiabl measures of technical performance, which can be used to compare actual results against targets. such technice performance measures may include weight, transaction times, number of delivered defects, storage capacity etc. deviation can indicate the potential impact of threats or opportunities. @ reserve analysis. described in section 7.2.2.6. throughout execution of the project, some individual project risks may occur with positive or negative impacts on budget or schedule contingency reserves. reserve analysis compares the amount of the contingency reserves remaining to the amount of risk remaining at any time in the project in order to determine if the remaining reserve is adequate. this may be communicated using various graphical representations, including a burndown chart. | data analysis technique that can be use for this process include but be not limit to : technical performance analysis . technical performance analysis compare technical accomplishment durinproject execution to the schedule of technical achievement . it require the definition of objective , quantifiablmeasures of technical performance , which can be use to compare actual result against target . such techniceperformance measure may include weight , transaction time , number of delivered defect , storage capacityetc . deviation can indicate the potential impact of threat or opportunity . reserve analysis . describe in section 7.2.2.6. throughout execution of the project , some individual projectrisks may occur with positive or negative impact on budget or schedule contingency reserve . reserve analysiscompares the amount of the contingency reserve remain to the amount of risk remain at any time in theproject in order to determine if the remain reserve be adequate . this may be communicate use variousgraphical representation , include a burndown chart .
109 | 11.7.2.2 audits | described in section 8.2.2.5. risk audits are a type of audit that may be used to consider the effectiveness of the ¦ management process. the project manager is responsible for ensuring that risk audits are performed at an appropri frequency, as defined in the project’s risk management plan. risk audits may be included during routine project rev meetings or may form part of a risk review meeting, or the team may choose to hold separate risk audit meetings. ' format for the risk audit and its objectives should be clearly defined before the audit is conducted. | describe in section 8.2.2.5. risk audit be a type of audit that may be use to consider the effectiveness of the ¦management process . the project manager be responsible for ensure that risk audit be perform at an approprifrequency , a define in the project ’ s risk management plan . risk audit may be include during routine project revmeetings or may form part of a risk review meeting , or the team may choose to hold separate risk audit meeting . 'format for the risk audit and it objective should be clearly define before the audit be conduct .
110 | 11.7.2.3 meetings | meetings that can be used during this process include but are not limited to risk reviews. risk reviews are scheduled regularly and should examine and document the effectiveness of risk responses in dealing with overall project risk and with identified individual project risks. risk reviews may also result in identification of new individual project risks, (including secondary risks that arise from agreed-upon risk responses), reassessment of current risks, the closing of risks that are outdated, issues that have arisen as the result of risks that have occurred, and identification of lessons to be learned for implementation in ongoing phases in the current project or in similar projects in the future. the risk review may be conducted as part of a periodic project status meeting or a dedicated risk review meeting may be held, as specified in the risk management plan. | meeting that can be use during this process include but be not limit to risk review . risk review be scheduledregularly and should examine and document the effectiveness of risk response in deal with overall project riskand with identified individual project risk . risk review may also result in identification of new individual project risk , ( include secondary risk that arise from agreed-upon risk response ) , reassessment of current risk , the closing ofrisks that be outdated , issue that have arise a the result of risk that have occur , and identification of lessonsto be learn for implementation in ongoing phase in the current project or in similar project in the future . the riskreview may be conduct a part of a periodic project status meeting or a dedicate risk review meeting may be hold , a specify in the risk management plan .
111 | 11.7.3 monitor risks: outputs
112 | 11.7.3.1 work performance information | described in section 4.5.1.3. work performance information includes information on how project risk managem is performing by comparing the individual risks that have occurred with the expectation of how they would occur. t information indicates the effectiveness of the response planning and response implementation processes. | describe in section 4.5.1.3. work performance information include information on how project risk managemis perform by compare the individual risk that have occur with the expectation of how they would occur . tinformation indicate the effectiveness of the response planning and response implementation process .
113 | 11.7.3.2 change requests | described in section 4.3.3.4. the monitor risks process may result in a change request to the cost and schedule baselines or other components of the project management plan. change requests are processed for review and disposition through the perform integrated change control process (section 4.6). change requests can include recommended corrective and preventive actions to address the current level project risk or to address individual project risks. | describe in section 4.3.3.4. the monitor risk process may result in a change request to the cost and schedulebaselines or other component of the project management plan . change request be process for review anddisposition through the perform integrated change control process ( section 4.6 ) .change request can include recommended corrective and preventive action to address the current levelproject risk or to address individual project risk .
114 | 11.7.3.3 project management plan updates | any change to the project management plan goes through the organization’s change control process via a change request. this may affect any component of the project management plan. | any change to the project management plan go through the organization ’ s change control process via a changerequest . this may affect any component of the project management plan .
115 | 11.7.3.4 project documents updates | @ assumption log. described in section 4.1.3.2. during the monitor risks process, new assumptions may be made, new constraints may be identified, and existing assumptions or constraints may be revisited and changed. the assumption log is updated with this new information. @ lessons learned register. described in section 4.4.3.1. the lessons learned register is updated with any risk-related lessons learned during risk reviews so these can be used on later phases of the project or in future projects. @ risk register. described in section 11.2.3.1. the risk register is updated with information on individual project risks generated during the monitor risks process. this may include adding new risks, updating outdated risks or risks that were realized, updating risk responses, and so forth. @ risk report. described in section 11.2.3.2. as new information becomes available through the monitor risks process, the risk report is updated to reflect the current status of major individual project risks and the current level of overall project risk. the risk report may also include details of the top individual project risks, agreed- upon responses and owners, and conclusions and recommendations. it may also include conclusions from risk audits on the effectiveness of the risk management nrocess. | assumption log . describe in section 4.1.3.2. during the monitor risk process , new assumption may bemade , new constraint may be identify , and exist assumption or constraint may be revisit and changed.the assumption log be update with this new information . lesson learn register . describe in section 4.4.3.1. the lesson learn register be update with anyrisk-related lesson learn during risk review so these can be use on late phase of the project or infuture project . risk register . describe in section 11.2.3.1. the risk register be update with information on individual projectrisks generate during the monitor risk process . this may include add new risk , update outdated risk orrisks that be realize , update risk response , and so forth . risk report . describe in section 11.2.3.2. a new information become available through the monitor risksprocess , the risk report be update to reflect the current status of major individual project risk and the currentlevel of overall project risk . the risk report may also include detail of the top individual project risk , agreed-upon response and owner , and conclusion and recommendation . it may also include conclusion from riskaudits on the effectiveness of the risk management nrocess .
116 | 11.7.3.5 organizational process assets updates | @ templates for the risk management plan, risk register, and risk report; and | template for the risk management plan , risk register , and risk report ; and